## Summary
Complaint Management System (CMS) v2.12-beta
Module | Pass | Fail | Skipped | Total | % Pass | % Fail
CMS | 166 | 4 | 5 | 175 | 94.86% | 2.286%
Automation | 168 | 14 | 7 | 189 | 88.89% | 7.407%

## Known Issues (v2.12-beta)
Title | URL | Assignees | Priority | Status
Ansible deploy: 9 fixes needed for fresh-box + repeat ethiopia deploys (2026-07-15 session) | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1245 | dhruv-1001 | P1 | Todo
[Bug] CMS: Employee: CSR user is able to reopen complaint even after the 1 hr reopen limit has lapsed on citizen ui | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/925 | dhruv-1001 | P1 | Todo
[Enhancement] Enable Matomo (needs scope + spec) | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1254 | singhalkarun | P1 | Todo
[Feature] [SaaS Enablement] Exemplify a SaaS demoable instance on a high-availability deployment, packaged on 2.12 | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1358 | singhalkarun | P1 | Todo
[Bug] Sync whatsapp Templates from twillio: Getting error for few messages | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1516 | ChakshuGautam | P1 | Todo
[Bug] Error encountered while creating the workflow in Novu | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1517 | singhalkarun | P1 | Todo
[Enhancement] Need to add default alert thresholds to Grafana | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1538 | singhalkarun | P1 | Todo
[Enhancement] Add missing seed data required by integration-tests | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1542 | dhruv-1001 | P1 | Todo
[Bug] egov-filestore fails to start due to Flyway baseline issue: Migration V20170420135841 reruns on existing schema | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1586 | singhalkarun | P1 | Todo
[Bug] Add localization for one department value in dashboard | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1590 | KDwevedi | P1 | Todo
[Bug] Complaints over time x-axis only in days | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1460 |  | P1 | Backlog
Enhancement: Improving testing suite | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1047 | dhruv-1001 | P1 | In progress
[Enhancement] Setup deployment using digit registry | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1309 | dhruv-1001 | P1 | In progress
[Task] Setup a grievance system to exemplify a demonstration to Indian authorities with detailing added to it | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1412 | Lokendra-egov | P1 | In progress
[Story] Allow a Windows native user to use the one click local installer to run through an install of CMS | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1423 | singhalkarun | P1 | In progress
[Bug] 0-1 configuration: Image fixes (move from flywheel to egov registry) | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1503 | dhruv-1001 | P1 | In progress
[Enhancement] Dashboard : Context addition for "Unknown" category in dashboard tiles | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1459 | Gurjeet-eGov | P1 | To Review
[Enhancement] CMS: Validate target admin level before populating OSM boundary level dropdown | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1016 | dhruv-1001 | P2 | Todo
Repurpose Nai Pepea as dev-cms-saas.digit.org — stable demoable instance | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1036 | dhruv-1001 | P2 | Todo
[Bug] Configurator: cannot create/edit several masters (Encryption Policy, Decryption ABAC, Security Policy, Inbox Config, UI Homepage, StateInfo) | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1250 | singhalkarun | P2 | Todo
[Enhancement] Vulnerability Testing | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1482 | singhalkarun, vinothrallapalli-eGov | P2 | Todo
[Bug]Dashboard: Flow ratio by department fixes | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1458 | KDwevedi | P2 | Todo
[Bug] Mobile number validation of 9 digits not working, ui accepts 10 digits starting with '7' | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1558 | KDwevedi | P2 | Todo
[Bug] Citizen login otp message is not logged in configurator ui notifications | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1559 | KDwevedi | P2 | Todo
[Enhancement] Notification after addition of new KPI's | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1463 |  | P2 | Backlog
[Bug] Fix CI on PRs — localization seed + tilt telemetry race | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1308 | dhruv-1001 | P2 | In progress
[Bug] Minor ui issue on onboarding flow Phase 2 of configurator ui | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1555 | KDwevedi | P3 | Todo
[Keycloak enablement] digit-ui-v2 fully functional under Google SSO — admin can configure their account, citizen can file a complaint e2e | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1357 | KDwevedi |  | Todo
[Enhancement] Publicly Accessible UI for Dashboard | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1540 | KDwevedi, rahuljose-egov |  | Todo

## CMS Automaiton (v2.12-beta)
Suite | Functionality | Test File | Test Case ID/playwright path | Test Scenario | Test Summary | Pre-requisites | Acceptance Criteria | Issue/Story Ref | Status | Notes
Citizen | Home / Landing | citizen-help-and-faq.spec.ts | Citizen aux surfaces — issue #12 regression guards › FAQ page does not render the error fallback | FAQ help page smoke | FAQ page loads without rendering the generic error fallback | Fresh citizen login | FAQ page body visible; no error-fallback component present | CCRS#12 | Pass
Citizen | Home / Landing | citizen-help-and-faq.spec.ts | Citizen aux surfaces — issue #12 regression guards › How-it-works page does not render the error fallback | How-it-works smoke | How-it-works page loads without error fallback | Fresh citizen login | How-it-works body visible; no error-fallback component | CCRS#12 | Pass
Citizen | Home / Landing | citizen-home-page.spec.ts | Citizen home + landing › /citizen/ redirects to /citizen/all-services | Root redirect | / redirects to /all-services | Authenticated citizen | URL resolves to /citizen/all-services | Story 2.1 | Pass
Citizen | Home / Landing | citizen-home-page.spec.ts | Citizen home + landing › /all-services renders CCRS title + File a Complaint + My Complaints links | All-services landing | All-services page shows CCRS title + action links | Fresh citizen OTP login | Body includes title; File a Complaint and My Complaints links present | Story 2.1 | Pass
Citizen | Home / Landing | citizen-home-page.spec.ts | Citizen home + landing › /pgr-home renders the PGR module home with action links | PGR home landing | PGR-branded home page renders actionable content | Suite-wide citizen login | Title, My Complaints, File a Complaint links present | Story 2.2 | Pass
Citizen | Home / Landing | citizen-home-page.spec.ts | Citizen home + landing › header language pill renders the current locale | Language pill | Header shows current locale label | Fresh citizen OTP login | label:has-text("English") visible within 5s | Story 2.3 | Pass
Citizen | Home / Landing | citizen-landing-dispatch.spec.ts | Citizen landing dispatch › smoke: lands on a usable citizen page | Landing dispatch smoke | Citizen landing page loads without crashing | Clean storage state | Detected landing mode is not 'unknown' within 15s |  | Pass
Citizen | Home / Landing | citizen-landing-dispatch.spec.ts | Citizen landing dispatch › dispatch: lands on the branch globalConfigs selects, and that branch works | Language selection dispatch | Language-selection surface renders and Continue navigates onward | Deployment with >1 configured language | Choose Language heading visible; clicking Continue routes forward |  | Pass
Citizen | Authentication | citizen-logout.spec.ts | citizen logout redirects to login page | Citizen logout | Logout redirects to /citizen/login | Authenticated citizen | Page URL ends with /citizen/login after logout | Story 9.1 | Pass
Citizen | Authentication | citizen-otp-login.spec.ts | Citizen Login › login page renders with mobile input | OTP login page render | Login page displays mobile number input | No prior session | Mobile input visible; Send OTP button present |  | Pass
Citizen | Authentication | citizen-otp-login.spec.ts | Citizen Login › citizen can log in with OTP and reach home page | OTP login flow | Citizen logs in with fixed OTP and reaches home page | OTP mock enabled | localStorage Citizen.token set; redirected to /all-services |  | Pass
Citizen | Profile | citizen-profile-page.spec.ts | Citizen profile field-set lock-down › only Name + Gender + Email + photo render | Profile fields lock-down | Profile page shows only allowed fields | Authenticated citizen | Name/Gender/Email/photo present; password/mobile/language absent |  | Pass
Citizen | Registration | citizen-registration.spec.ts | Citizen registration (auto-register on unknown number) › fresh phone → OTP → name+email → /all-services | New citizen registration | Unknown phone auto-registers on OTP flow | No prior registration for the number | Lands on /all-services after name+email step |  | Pass
Citizen | Complaint Filing | complaint-attachment.spec.ts | citizen complaint — attachment lifecycle #555 › upload preview renders, then detail page surfaces the same image | Attachment upload | Image upload preview renders; same image shown on detail page | Authenticated citizen | Upload preview visible; detail page img src matches | CCRS#555 | Pass
Citizen | Complaint Filing | complaint-create-payload-contract.spec.ts | 03-citizen-create: PGR _create payload completeness (#478 + #72) › digit-ui bundle declares AddressOne + AddressTwo populators | Payload completeness | Bundle declares AddressOne + AddressTwo populators | None | JS bundle contains AddressOne + AddressTwo strings | CCRS#478 | Pass
Citizen | Complaint Filing | complaint-create-payload-contract.spec.ts | 03-citizen-create: pincode validation (#478) › the deployment postal-code pattern accepts this tenant's valid sample and rejects malformed input | Postal code validation | Tenant postal-code pattern accepts valid sample; rejects malformed | None | valid sample passes; malformed input rejected | CCRS#478 | Pass
Citizen | Complaint Filing | complaint-create-payload-contract.spec.ts | 03-citizen-create: pincode validation (#478) › the legacy Indian pattern would have rejected this tenant's valid postal code | Legacy pattern check | Legacy Indian postal pattern would reject tenant's valid code | None | Expected legacy pattern to reject the tenant sample | CCRS#478 | Pass
Citizen | Complaint Filing | complaint-create-payload-contract.spec.ts | 03-citizen-create: pincode validation (#478) › the discovered postal pattern is self-consistent with the deployment's own globalConfigs | Pattern self-consistency | Discovered postal pattern matches globalConfigs | None | Pattern matches globalConfigs postal value | CCRS#478 | Pass
Citizen | Complaint Detail | complaint-detail-page.spec.ts | complaint details page loads without crashing for a freshly-filed complaint | Detail page load | Citizen complaint detail page loads without JS error | Freshly filed complaint | Detail heading and complaint ID visible |  | Pass
Citizen | Complaint Detail | complaint-timeline-and-rating-display.spec.ts | 04-citizen-timeline (#473 follow-up) › PGR _search returns service.rating + workflow.action=RATE for the rated complaint | Timeline rating API | _search response includes service.rating and RATE action | Rated complaint fixture | Response body contains service.rating and action=RATE | CCRS#473 | Pass
Citizen | Complaint Detail | complaint-timeline-and-rating-display.spec.ts | 04-citizen-timeline (#473 follow-up) › Localization keys for the timeline rendering are seeded across the deployment locales | Timeline localization | Timeline localization keys seeded in all deployment locales | None | rainmaker-common and rainmaker-pgr contain timeline keys | CCRS#473 | Pass
Citizen | Complaint Filing | complaint-type-dropdown-labels.spec.ts | complaint type dropdown shows human-readable translated names | Dropdown labels | Complaint type dropdown shows translated names, not raw keys | Authenticated citizen | Dropdown options show human-readable labels |  | Pass
Citizen | Complaint Filing | file-complaint-wizard.spec.ts | Citizen file-complaint wizard › walks 6 steps + submits + lands on /pgr/response with PGR ID | File complaint wizard | Walks 6 steps; submits; lands on response page with PGR ID | Authenticated citizen | /pgr/response page shows PGR complaint ID |  | Pass
Citizen | Complaint Filing | file-complaint-wizard.spec.ts | Citizen file-complaint wizard › no raw localization keys visible at any wizard step | Wizard localization | No raw i18n keys visible at any wizard step | Authenticated citizen; localizations seeded | All labels show translated text; no RAINMAKER_ keys visible |  | Fail | Raw i18n key(s) visible at one or more wizard steps — localization not seeded
Citizen | Full Lifecycle | full-complaint-lifecycle-ui.spec.ts | PGR lifecycle — UI only › 1 — citizen logs in via UI with fixed OTP | Lifecycle step 1: login | Citizen logs in via UI with fixed OTP | OTP mock; clean session | localStorage Citizen.token set |  | Pass
Citizen | Full Lifecycle | full-complaint-lifecycle-ui.spec.ts | PGR lifecycle — UI only › 2 — citizen creates complaint via UI wizard | Lifecycle step 2: create | Citizen creates complaint via wizard | Step 1 passed | Complaint created; PGR ID on response page |  | Pass
Citizen | Full Lifecycle | full-complaint-lifecycle-ui.spec.ts | PGR lifecycle — UI only › 3 — admin sees complaint in PGR inbox (UI) | Lifecycle step 3: admin inbox | Admin sees new complaint in PGR inbox | Step 2 passed | Complaint row visible in admin inbox |  | Pass
Citizen | Full Lifecycle | full-complaint-lifecycle-ui.spec.ts | PGR lifecycle — UI only › 4 — admin assigns complaint via UI | Lifecycle step 4: assign | Admin assigns complaint via Take Action modal | Step 3 passed | Status transitions to PENDINGATLME |  | Fail | ASSIGN action failed — Take Action modal did not complete within timeout
Citizen | Full Lifecycle | full-complaint-lifecycle-ui.spec.ts | PGR lifecycle — UI only › 5 — admin resolves complaint via UI | Lifecycle step 5: resolve | Admin resolves complaint via Take Action | Step 4 passed | Status transitions to RESOLVED |  | NA (Skipped) | Skipped — dependent on step 4 (admin assigns) which failed
Citizen | Full Lifecycle | full-complaint-lifecycle-ui.spec.ts | PGR lifecycle — UI only › 6 — citizen sees resolved complaint on complaints page (UI) | Lifecycle step 6: citizen view | Citizen sees resolved complaint | Step 5 passed | Complaint shows RESOLVED status on My Complaints |  | NA (Skipped) | Skipped — dependent on step 4 (admin assigns) which failed
Citizen | Authentication | login-mobile-input-validation.spec.ts | citizen login mobile validation — #429 › 5-digit number shows inline error + helper hint | Mobile validation | 5-digit number triggers inline error + persistent helper hint | No session | Inline error message visible; helper hint persists | CCRS#429 | Pass
Citizen | Home / Landing | pgr-home-layout-and-scroll.spec.ts | citizen PGR regression — shipped fixes › #421 — landing ServicesSection top padding matches side padding | Layout regression #421 | ServicesSection top padding matches side padding | Authenticated citizen | CSS padding values equal | CCRS#421 | Pass
Citizen | Home / Landing | pgr-home-layout-and-scroll.spec.ts | citizen PGR regression — shipped fixes › #422 — navigating into Create New Complaint lands at top of page | Scroll regression #422 | Navigating to complaint creation lands at page top | Authenticated citizen | window.scrollY === 0 after navigation | CCRS#422 | Pass
Citizen | Home / Landing | pgr-home-layout-and-scroll.spec.ts | citizen PGR regression — shipped fixes › #441 — submit rating without "What was good?" boxes does not crash | Rating crash #441 | Rating submission without feedback checkboxes does not crash | Authenticated citizen; resolved complaint | No JS error on submit; page still responsive | CCRS#441 | Pass
Citizen | Complaint Filing | postal-code-alnum-input.spec.ts | Citizen v2 postal-code input — alnum/dash regression (PR #1315) › postal-code field retains alnum + dash characters instead of stripping them | Postal alnum regression | Postal code field retains alnum + dash input | Authenticated citizen | Field value unchanged after typing alnum+dash | CCRS#722 | Fail | Postal code field stripped alnum/dash characters; #722 regression
Citizen | Complaint Filing | postal-code-alnum-input.spec.ts | Citizen v2 postal-code input — alnum/dash regression (PR #1315) › invalid postal code renders the length-interpolated localized error | Postal error message | Invalid postal code shows length-interpolated error | Authenticated citizen | Error message contains interpolated min/max length | CCRS#722 | Pass
Citizen | Profile | profile-photo-save-445.spec.ts | citizen profile — photo save round-trip #445 (JPEG) › upload JPEG photo, _update returns 2xx, no hard reload | Profile photo JPEG | JPEG photo upload round-trips via _update without hard reload | Authenticated citizen | _update response 2xx; no full page reload | CCRS#445 | Pass
Citizen | Profile | profile-photo-save.spec.ts | citizen profile — photo save round-trip #556 › upload photo, _update returns 2xx, no hard reload | Profile photo save | Photo upload round-trips via _update without hard reload | Authenticated citizen | _update response 2xx; no full page reload | CCRS#556 | Pass
Citizen | Complaint Detail | rate-resolved-complaint.spec.ts | Citizen rate-complaint UI › rate page renders 5 stars + 4 feedback checkboxes + Comments textarea | Rate complaint UI | Rating page shows 5 stars + 4 checkboxes + Comments | Authenticated citizen; RESOLVED complaint | 5 star inputs; 4 checkbox options; Comments textarea visible |  | Pass
Citizen | Complaint Detail | reopen-closed-complaint.spec.ts | Citizen reopen-complaint UI › reopen step 0 renders title + 4 reason radios + Next button | Reopen complaint UI | Reopen page shows title + 4 reason radios + Next | Authenticated citizen; RESOLVED complaint | Title, 4 radio buttons, Next button visible |  | Pass
Citizen | Complaint Tracking | track-my-complaint.spec.ts | Citizen track-complaint › My Complaints list shows the seeded complaint with OPEN badge | My Complaints list | My Complaints shows seeded complaint with OPEN badge | Authenticated citizen; seeded complaint | Complaint row with OPEN status badge visible |  | Pass
Citizen | Complaint Tracking | track-my-complaint.spec.ts | Citizen track-complaint › Detail page renders Summary / Details / Map / Timeline sections | Detail sections | Complaint detail renders all 4 sections | Authenticated citizen; seeded complaint | Summary, Details, Map, Timeline sections all visible |  | Pass
Citizen | Complaint Tracking | track-my-complaint.spec.ts | Citizen track-complaint › Detail URL uses /complaints/:id (PLURAL) — Routes.js export diverges | Detail URL format | Detail URL uses /complaints/:id (plural) | Authenticated citizen | URL path contains /complaints/ (plural) |  | Pass
Citizen | Complaint Filing | wizard-pin-and-boundary-cascade.spec.ts | 06-citizen-pin-and-cascade — PR #74 regression › pin step + locality cascade no longer trap the citizen | Pin + boundary cascade | Pin step and locality cascade work without trapping citizen | Authenticated citizen | Pin step completes; locality dropdown populates; no infinite spinner | CCRS#74 | Pass
Employee | Profile | change-password-visibility-812.spec.ts | employee profile — change password button visibility #812 › Change Password button styling check | Change Password button style | Change Password button has correct Tailwind styling | Authenticated employee | Button carries expected CSS classes and computed styles | #812 | Pass
Employee | UI Shell | digit-ui-shell-2026-05-31.spec.ts | employee digit-ui shell bundle › login + chrome + visible decrypt + inbox honest drives | Shell bundle integrity | Login, chrome, decrypt toggle, inbox drives all work end-to-end | Authenticated employee | Banner logo loads; inbox rows visible; decrypt button present |  | Fail | Banner logo naturalWidth=0 — image failed to load (#505)
Employee | Workflow Actions | escalate-action-521.spec.ts | employee — manual Escalate action #521 › PENDINGATLME → Escalate → real ESCALATE transition into the configured target state | Escalate action | ESCALATE action transitions complaint to configured target state | PENDINGATLME complaint; BOMET_LME persona | Complaint moves to PENDINGATSUPERVISOR via ESCALATE | #521 | Pass
Employee | Inbox | inbox-filters.spec.ts | employee inbox-v2 — filters narrow the result set › status filter → only rows in the chosen workflow state @p0 | Inbox status filter | Status filter shows only rows in selected workflow state | Authenticated employee; seeded complaints | Filtered rows all show selected status |  | Pass
Employee | Inbox | inbox-filters.spec.ts | employee inbox-v2 — filters narrow the result set › complaint-type filter → only rows of the chosen serviceCode @p0 | Inbox type filter | Complaint-type filter shows only rows of chosen serviceCode | Authenticated employee; seeded complaints | All rows match selected serviceCode |  | NA (Skipped)
Employee | Inbox | inbox-filters.spec.ts | employee inbox-v2 — filters narrow the result set › locality filter → only rows in the chosen leaf boundary @p0 | Inbox locality filter | Locality filter shows only rows in chosen boundary | Authenticated employee; seeded complaints | All rows match selected locality |  | NA (Skipped)
Employee | Inbox | inbox-search.spec.ts | employee inbox-v2 — search › search by complaint number returns exactly that complaint @p1 | Search by complaint no. | Search by complaint number returns exactly that row | Authenticated employee; seeded complaint | Exactly 1 row matching the complaint number |  | Pass
Employee | Inbox | inbox-search.spec.ts | employee inbox-v2 — search › search by mobile number returns the matching complaint @p1 | Search by mobile | Search by mobile returns matching complaint | Authenticated employee; seeded complaint | Row with matching mobile number visible |  | Pass
Employee | Inbox | inbox-search.spec.ts | employee inbox-v2 — search › search for a well-formed but non-existent complaint number returns nothing @p1 | Search no results | Search for non-existent complaint returns empty result | Authenticated employee | Empty state shown; 0 rows returned |  | Pass
Employee | Authentication | login.spec.ts | Employee Login — API › valid credentials return access token | Employee login API | Valid credentials return access token | None | Response contains accessToken |  | Pass
Employee | Authentication | login.spec.ts | Employee Login — API › bad credentials are rejected | Bad credentials rejected | Bad credentials return error response | None | Response 400/401 with error message |  | Pass
Employee | Authentication | login.spec.ts | Employee Login — UI › API session injection loads employee home | Session injection | API token injected into localStorage loads employee home | None | Employee home page visible after token injection |  | Pass
Employee | Complaint Detail | pgr-details.spec.ts | PGR complaint details — Flow 5 render slice › Story 5.1 — details page loads without error (terminal fixture) @p0 | Detail page load | Complaint detail page loads without error | Terminal complaint fixture | Detail page renders; no error state |  | Pass
Employee | Complaint Detail | pgr-details.spec.ts | PGR complaint details — Flow 5 render slice › Story 5.4 — Complaint No. label + value match the SRID @p0 | Complaint No. field | Complaint No. label shows the SRID value | Terminal complaint fixture | Label + value match expected SRID |  | NA (Skipped)
Employee | Complaint Detail | pgr-details.spec.ts | PGR complaint details — Flow 5 render slice › Story 5.5 — Current Status chip renders localized status text @p0 | Status chip | Status chip renders localized status text | Terminal complaint fixture | Chip shows localized status string |  | NA (Skipped)
Employee | Complaint Detail | pgr-details.spec.ts | PGR complaint details — Flow 5 render slice › Story 5.6 — complaint classification rows render localized values @p1 | Classification rows | Classification rows (type/subtype/category) show localized values | Terminal complaint fixture | All classification labels and values localized |  | NA (Skipped)
Employee | Complaint Detail | pgr-details.spec.ts | PGR complaint details — Flow 5 render slice › Story 5.9 — Filed Date renders in DD/MM/YYYY @p1 | Filed date format | Filed Date renders in DD/MM/YYYY format | Terminal complaint fixture | Date value matches DD/MM/YYYY pattern |  | Pass
Employee | Complaint Detail | pgr-details.spec.ts | PGR complaint details — Flow 5 render slice › Story 5.16 — Complaint Timeline section renders with checkpoint rows @p0 | Timeline section | Timeline section renders with at least one checkpoint row | Terminal complaint fixture | Timeline section visible with ≥1 checkpoint |  | Pass
Employee | Complaint Detail | pgr-details.spec.ts | PGR complaint details — Flow 5 render slice › Story 5.18 — timeline actor name is clean (no role-list concat) — #524 | Timeline actor name | Timeline actor name is clean employee name, not role list | Terminal complaint fixture | Actor name does not contain comma-separated role list | #524 | Pass
Employee | Complaint Detail | pgr-details.spec.ts | PGR complaint details — Flow 5 render slice › Story 5.24a — Take Action HIDDEN on terminal-state complaint @p1 | Take Action hidden | Take Action button hidden on terminal complaint | Terminal complaint fixture | Take Action button absent from DOM |  | Pass
Employee | Complaint Detail | pgr-details.spec.ts | PGR complaint details — Flow 5 render slice › Story 5.24b — Take Action VISIBLE on non-terminal complaint @p0 | Take Action visible | Take Action button visible on non-terminal complaint | Non-terminal complaint fixture | Take Action button present and clickable |  | Pass
Employee | Workflow | pgr-fixes-2026-04-29.spec.ts | 02-pgr-employee: assign + workflow guards (#479 + follow-ups) › PGR business service: PENDINGFORASSIGNMENT.ASSIGN forward-state is PENDINGATLME, not a self-loop | Assign forward state | ASSIGN transitions to PENDINGATLME, not self-loop | None | Workflow response shows nextState=PENDINGATLME | CCRS#479 | Pass
Employee | Workflow | pgr-fixes-2026-04-29.spec.ts | 02-pgr-employee: assign + workflow guards (#479 + follow-ups) › PGR_LME-only role filter returns LMEs (not all-of-HRMS) | LME role filter | Role filter returns only LMEs, not all HRMS employees | None | Response list contains only LME-role employees | CCRS#479 | Pass
Employee | Workflow | pgr-fixes-2026-04-29.spec.ts | 02-pgr-employee: assign + workflow guards (#479 + follow-ups) › REJECTED state advertises a non-empty rejection-reason mdms list | Rejection reasons MDMS | MDMS RejectionReasons list is non-empty for REJECTED state | None | mdms RejectionReasons.length > 0 | CCRS#479 | Fail | MDMS RejectionReasons list empty — not seeded on this tenant
Employee | Inbox | pgr-inbox-sort-922.spec.ts | employee inbox-v2 — column header sort (issue #922) › clicking Locality sorts ascending server-side, by the raw code, with no page error @p0 | Locality sort ascending | Clicking Locality header sorts ascending server-side | Authenticated employee | XHR sortBy=locality&sortOrder=ASC; no page error | #922 | Pass
Employee | Inbox | pgr-inbox-sort-922.spec.ts | employee inbox-v2 — column header sort (issue #922) › clicking Locality again toggles to descending, in both the request and the row order @p0 | Locality sort descending | Second click on Locality toggles to descending | Authenticated employee | XHR sortBy=locality&sortOrder=DESC; rows in desc order | #922 | Pass
Employee | Inbox | pgr-inbox-sort-922.spec.ts | employee inbox-v2 — column header sort (issue #922) › the sort icon toggles direction across repeated clicks, instead of staying on one arrow @p0 | Sort icon toggle | Sort icon arrow direction toggles on repeated clicks | Authenticated employee | Arrow icon changes direction on each click | #922 | Pass
Employee | Inbox | pgr-inbox-sort-922.spec.ts | employee inbox-v2 — column header sort (issue #922) › "Current Owner" has no sort affordance — pgr-services has no sort-by equivalent for it @p0 | No sort on Current Owner | Current Owner column header has no sort button/icon | Authenticated employee | No sort affordance present on Current Owner header | #922 | Pass
Employee | Profile | profile-validation-config-445.spec.ts | employee profile — validationConfig null-safety #445 › post-auth UserProfile mount + onChange do not throw | Profile null safety | UserProfile mounts and onChange fires without throwing | Authenticated employee | No JS exception on mount or onChange event | #445 | Pass
Employee | Profile | profile.spec.ts | employee profile — country prefix #444 › mobile prefix chip renders the tenant dial code (not hardcoded +91) | Dial code chip | Mobile prefix chip shows tenant dial code, not +91 | Authenticated employee | Chip shows +254 (Kenya); not +91 | #444 | Pass
Employee | Complaint Management | reopen-limit-925.spec.ts | Employee PGR reopen window is driven by MDMS REOPENSLA #925 › blocks reopen and shows a toast once the configured window has elapsed | Reopen window expired | App blocks reopen and shows toast after SLA window elapses | Complaint resolved before REOPENSLA expired | Reopen button disabled/hidden; toast message shown | #925 | Pass
Employee | Complaint Management | reopen-limit-925.spec.ts | Employee PGR reopen window is driven by MDMS REOPENSLA #925 › allows reopen while still inside the configured window | Reopen window active | App allows reopen while inside SLA window | Recently resolved complaint | Reopen button active and accessible | #925 | Pass
Employee | UI Shell | sidebar.spec.ts | employee shell chrome › HRMS + Workbench are absent from the employee shell | HRMS/Workbench hidden | HRMS and Workbench modules absent from employee sidebar | Authenticated employee | HRMS and Workbench nav links not present | CCRS#560,CCRS#561 | Pass
Employee | UI Shell | sidebar.spec.ts | employee shell chrome › sidebar drops modules listed in EMPLOYEE_MODULE_DENYLIST | Denylist modules hidden | Denylist modules not shown in employee sidebar | Authenticated employee | Modules in EMPLOYEE_MODULE_DENYLIST absent from sidebar | CCRS#446 | Fail | DNS failure (getaddrinfo EAI_AGAIN) — network intermittent during run
Employee | Workflow | workflow-lifecycle-ui.spec.ts | employee PGR lifecycle through the Take-Action UI › ASSIGN (GRO) → PENDINGATLME, then RESOLVE (LME) → RESOLVED @p0 | Full lifecycle UI | GRO assigns → LME resolves via Take Action UI | Authenticated GRO and LME personas | Status transitions: PENDINGFORASSIGNMENT → PENDINGATLME → RESOLVED |  | Pass
Employee | Workflow | workflow-reject-ui.spec.ts | employee PGR REJECT through the Take-Action UI › REJECT (GRO) with a rejection reason → REJECTED, reason on timeline @p0 | Reject lifecycle UI | GRO rejects complaint with reason; reason appears on timeline | Authenticated GRO persona | Status=REJECTED; rejection reason visible in timeline |  | Pass
Admin | Boundary Management | boundaries-ui.spec.ts | manage/boundaries — list reflects boundaries created via wizard › search returns both PW-prefixed boundaries created through onboarding | Boundary search | Search returns PW-prefixed boundaries created via onboarding wizard | Onboarding wizard run | Both PW-prefixed boundaries appear in search results |  | Pass
Admin | Boundary Management | boundary-hierarchies.spec.ts | manage/boundary-hierarchies › 1. list renders with hierarchy type + levels columns | Hierarchy list | List renders with hierarchy type and levels columns | Authenticated admin | Columns HierarchyType and Levels visible; ≥1 row |  | Pass
Admin | Boundary Management | boundary-hierarchies.spec.ts | manage/boundary-hierarchies › 2. UI create happy path — chain of 2 levels shows up in list + API | Hierarchy create | Create hierarchy with 2 levels; appears in list and API | Authenticated admin | New hierarchy row in UI; API returns the record |  | Pass
Admin | Boundary Management | boundary-hierarchies.spec.ts | manage/boundary-hierarchies › 3. show page renders levels in chain order | Hierarchy show page | Show page renders levels in chain order | Authenticated admin | Level rows appear in correct parent→child order |  | Pass
Admin | Boundary Management | boundary-hierarchies.spec.ts | manage/boundary-hierarchies › 4. duplicate hierarchyType is rejected with DUPLICATE_RECORD | Duplicate hierarchy | Duplicate hierarchyType rejected with DUPLICATE_RECORD | Existing hierarchy | API returns DUPLICATE_RECORD error |  | Pass
Admin | Boundary Management | boundary-hierarchies.spec.ts | manage/boundary-hierarchies › 5. validation — empty hierarchyType blocks client-side submit | Hierarchy validation | Empty hierarchyType blocks form submit | Authenticated admin | Submit button inactive; inline validation visible |  | Pass
Admin | Boundary Management | boundary-hierarchies.spec.ts | manage/boundary-hierarchies › 6. API response shape — BoundaryHierarchy comes back as an array | Hierarchy API shape | BoundaryHierarchy API returns an array | None | Response body is an array |  | Pass
Admin | Complaint Management | complaint-form-validators-2026-05-31.spec.ts | admin complaint create — validator bundle 2026-05-30 › users + edit + create + validators bidirectional | Validator bundle | Admin create/edit forms have bidirectional validators | Authenticated admin | Inline validation fires on blur and submit in both directions |  | Fail | Test timeout 120s — bidirectional validator flow did not complete
Admin | Complaint Types | complaint-types.spec.ts | manage/complaint-types › 1. list renders with Service Code / Name / Department / SLA / Status columns | Complaint types list | List renders with all required columns | Authenticated admin | All 5 columns present; ≥1 row |  | Pass
Admin | Complaint Types | complaint-types.spec.ts | manage/complaint-types › 2. create → edit → deactivate round-trip; visible at city tenant | Complaint type CRUD | Create → edit → deactivate round-trip; visible at city tenant | Authenticated admin | Record created, edited, deactivated; visible at city tenant |  | Fail | Create-edit-deactivate round-trip failed; city-tenant visibility assertion failed
Admin | Complaint Types | complaint-types.spec.ts | manage/complaint-types › 4. department reference filter narrows the list | Department filter | Department filter narrows complaint types list | Authenticated admin | Visible rows all reference the selected department |  | Pass
Admin | Complaint Types | complaint-types.spec.ts | manage/complaint-types › 5. tenant parity — api create at root is visible at city tenant | Tenant parity | Complaint type created at root visible at city tenant | Authenticated admin | API search at city tenant returns the root-created record |  | Fail | Complaint type created at root not visible at city tenant
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 1. file complaint — citizen, locality, required landmark | File complaint | File complaint with citizen, locality, required landmark | Authenticated admin | Complaint created; confirmation page shown |  | Fail | pickLocality: no hierarchy/type combination yielded a selectable boundary
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 2. edit merges description + workflow ASSIGN in one round-trip | Edit + assign | Edit description and ASSIGN in one round-trip | Authenticated admin; PENDINGFORASSIGNMENT complaint | Single _update call; status → PENDINGATLME |  | Pass
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 3. workflow dropdown labels are human-readable, not UUIDs | Workflow labels | Workflow dropdown shows human-readable labels | Authenticated admin | Labels are localized strings, not UUID values |  | Pass
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 4. source select offers only Web/Mobile/WhatsApp | Source options | Source select shows Web/Mobile/WhatsApp only | Authenticated admin | Exactly 3 source options present |  | Pass
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 5. list footer count matches /pgr-services/v2/request/_count | Footer count | List footer count matches API _count response | Authenticated admin | Footer number equals _count API response value |  | Pass
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 6. status filter fires as an XHR query param | Status filter XHR | Status filter fires as XHR query param | Authenticated admin | Network request includes applicationStatus param |  | Pass
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 6b. From-date filter fires as a fromDate XHR query param | From-date filter XHR | From-date filter fires as fromDate XHR param | Authenticated admin | Network request includes fromDate param |  | Pass
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 7. department filter narrows visible rows | Department filter | Department filter narrows visible rows | Authenticated admin | All visible rows belong to selected department |  | Pass
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 8. show page renders address extras and a working geo link | Show page address | Show page renders address extras and geo link | Authenticated admin; complaint with address | Address fields and clickable geo link present |  | Pass
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 9. mobile-only citizen heuristic shows suffix on Show page | Mobile suffix | Mobile-only citizen shows suffix on show page | Authenticated admin | Citizen identifier shows expected suffix format |  | Pass
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 10. real pagination — offset-based _search fires with page 2 nav, not client-slice of first 100 | Pagination | Page 2 nav fires offset-based _search, not client-slice | Authenticated admin | Network request includes offset param for page 2 |  | Pass
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 11. department column renders the readable department name, not a raw code | Department name | Department column shows readable name, not raw code | Authenticated admin | Department column values are localized names |  | Pass
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 12. edit saves description + workflow in a single _update round-trip | Edit round-trip | Edit saves description + workflow in single _update | Authenticated admin | Exactly one _update API call containing both fields |  | Pass
Admin | Complaint Management | complaints.spec.ts | manage/complaints › 13. PENDINGFORASSIGNMENT filter returns the expected queue size | PENDINGFORASSIGNMENT queue | PENDINGFORASSIGNMENT filter returns expected count | Authenticated admin; seeded complaints | Visible row count matches expected queue size |  | Fail | Filter returned unexpected queue size
Admin | MDMS / Configurator | configurator-mdms-fixes-2026-04-29.spec.ts | 01-configurator-mdms: Department CRUD (#472 + follow-ups) › Department create REJECTS the legacy `description` field | Dept schema — legacy field | Department create rejects `description` field | None | API returns error when description field included | CCRS#472 | Pass
Admin | MDMS / Configurator | configurator-mdms-fixes-2026-04-29.spec.ts | 01-configurator-mdms: Department CRUD (#472 + follow-ups) › Department create with only schema-allowed fields SUCCEEDS | Dept schema — valid create | Department create with allowed fields succeeds | None | API returns 200 with created record | CCRS#472 | Pass
Admin | MDMS / Configurator | configurator-mdms-fixes-2026-04-29.spec.ts | 01-configurator-mdms: Department CRUD (#472 + follow-ups) › Department update with leaked `_isActive` / `_uniqueIdentifier` / `id` is REJECTED by MDMS | Dept schema — leaked fields | Dept update with leaked internal fields rejected by MDMS | None | API returns error for _isActive/_uniqueIdentifier/id fields | CCRS#472 | Pass
Admin | MDMS / Configurator | configurator-mdms-fixes-2026-04-29.spec.ts | 01-configurator-mdms: ComplaintType schema sanity › ComplaintHierarchy schema declares keywords / order / parentCode | ComplaintHierarchy schema | ComplaintHierarchy schema declares required fields | None | Schema contains keywords, order, parentCode properties | CCRS#472 | Pass
Admin | MDMS / Configurator | configurator-mdms-fixes-2026-04-29.spec.ts | 01-configurator-mdms: dataProvider create needs same sanitize as update › mdmsCreate REJECTS the same `_isActive` / `id` leak | mdmsCreate sanitize | mdmsCreate rejects same leaked fields as mdmsUpdate | None | API rejects _isActive/id in create payload | CCRS#472 | Pass
Admin | Department Management | departments.spec.ts | manage/departments › 1. list renders with header columns and filters narrow to the expected rows | Dept list | Dept list renders; filters narrow rows | Authenticated admin | Headers present; filter reduces visible rows |  | Pass
Admin | Department Management | departments.spec.ts | manage/departments › 2. single create → edit → deactivate round-trip | Dept CRUD | Create → edit → deactivate round-trip | Authenticated admin | Record goes through full lifecycle |  | Pass
Admin | Department Management | departments.spec.ts | manage/departments › 3. bulk import — happy path creates 5 rows | Dept bulk import | Bulk import creates 5 rows successfully | Authenticated admin | 5 new department rows appear in list |  | Pass
Admin | Department Management | departments.spec.ts | manage/departments › 4. bulk import — duplicate code rejected client-side | Bulk import duplicate | Bulk import rejects duplicate department code client-side | Authenticated admin | Client-side error for duplicate code |  | Pass
Admin | Department Management | departments.spec.ts | manage/departments › 5a. Show page renders "Related" reverse references (complaint-types + employees) | Dept show — related | Show page renders Related complaint-types and employees | Authenticated admin | Related sections visible with linked records |  | Pass
Admin | Department Management | departments.spec.ts | manage/departments › 5b. deactivation guard probes designation + employee APIs | Deactivation guard | Deactivation guard checks designation + employee APIs | Authenticated admin | Guard API calls fire before deactivation allowed |  | Pass
Admin | Department Management | departments.spec.ts | manage/departments › 5c. API update round-trip preserves auditDetails on a department | Audit details preserved | Update preserves auditDetails on department record | Authenticated admin | auditDetails unchanged after update |  | Pass
Admin | Department Management | departments.spec.ts | manage/departments › 6. bulk export round-trip — downloaded xlsx parses | Dept bulk export | Bulk export downloads parseable xlsx | Authenticated admin | Downloaded file parses as valid xlsx |  | Pass
Admin | Designation Management | designations.spec.ts | manage/designations › 1. create with multi-department persists as a string[] | Designation create | Create designation with multi-dept persists as string[] | Authenticated admin | API stores department as string[] not string |  | Pass
Admin | Designation Management | designations.spec.ts | manage/designations › 2. edit round-trip preserves array shape (add then remove) | Designation edit | Edit round-trip preserves department array shape | Authenticated admin | Array shape preserved after add and remove |  | Pass
Admin | Designation Management | designations.spec.ts | manage/designations › 4. department filter narrows list to designations referencing that code | Designation dept filter | Department filter narrows designation list | Authenticated admin | All visible designations reference selected dept code |  | Pass
Admin | Designation Management | designations.spec.ts | manage/designations › 5. deactivation guard counts dependent records | Designation deactivation guard | Deactivation guard counts employees on this designation | Authenticated admin | Guard shows dependent employee count |  | Pass
Admin | Designation Management | designations.spec.ts | manage/designations › 5a. department chip input dropdown loads options from mdms | Dept chip dropdown | Dept chip input dropdown loads MDMS department options | Authenticated admin | Dropdown options populated from MDMS |  | Pass
Admin | Designation Management | designations.spec.ts | manage/designations › 5b. show page renders department chips for a multi-dept designation | Designation show chips | Show page renders department chips | Authenticated admin | Department chip elements visible on show page |  | Pass
Admin | Designation Management | designations.spec.ts | manage/designations › 5c. API soft-delete (isActive=false) removes row from active list | Designation soft-delete | isActive=false removes row from active list | Authenticated admin | Deactivated row absent from active list |  | Pass
Admin | Designation Management | designations.spec.ts | manage/designations › 5d. HRMS probe returns assignments.designation for guard counter | HRMS probe | HRMS probe returns assignments.designation for guard | Authenticated admin | Response contains assignments.designation |  | Pass
Admin | Designation Management | designations.spec.ts | manage/designations › 6. bulk import accepts comma-list department values as array | Designation bulk import | Bulk import accepts comma-list dept values as array | Authenticated admin | Imported records store department as array |  | Pass
Admin | Employee Management | employee-create-tenant-459.spec.ts | admin employee create — tenant + form-clears #459 #471 #476 › fills the create form and submits — tenant correct + form clears | Employee create | Create employee form submits with correct tenant; form clears after | Authenticated admin | Employee created at correct tenant; form fields clear | #459,#471,#476 | Fail | Form submit failed — tenant/form-clears assertion failed (#459)
Admin | Employee Management | employee-mobile-validator-447.spec.ts | admin employee create — mobile validator (MDMS rule) #447 #674 › valid mobile clears aria-invalid | Valid mobile validation | Valid mobile clears aria-invalid attribute | Authenticated admin | aria-invalid removed after valid mobile input | #447,#674 | Pass
Admin | Employee Management | employee-mobile-validator-447.spec.ts | admin employee create — mobile validator (MDMS rule) #447 #674 › invalid mobile surfaces help text and aria-invalid | Invalid mobile validation | Invalid mobile shows help text and aria-invalid | Authenticated admin | aria-invalid set; help text visible for invalid input | #447,#674 | Pass
Admin | Employee Management | employee-mobile-validator-447.spec.ts | admin employee create — mobile validator (MDMS rule) #447 #674 › second valid mobile candidate clears aria-invalid — #674 fallback | Fallback mobile validation | Second valid mobile pattern clears aria-invalid (#674) | Authenticated admin | aria-invalid cleared for fallback valid pattern | #674 | Pass
Admin | Employee Management | employees.spec.ts | manage/employees › 1. list renders; search narrows to the matching row; Status filter partitions the list | Employee list | List renders; search narrows; Status filter partitions | Authenticated admin | Search and filter produce correct subsets |  | Pass
Admin | Employee Management | employees.spec.ts | manage/employees › 2. single create — happy path derives code + username, employee lands | Employee create happy path | Create employee; code and username auto-derived; employee lands | Authenticated admin | New employee visible in list with auto-derived fields |  | Pass
Admin | Employee Management | employees.spec.ts | manage/employees › 3. too-short mobile shows inline validation error | Mobile too short | Too-short mobile number shows inline validation error | Authenticated admin | Inline error message visible for short mobile |  | Pass
Admin | Employee Management | employees.spec.ts | manage/employees › 4. edit — DOB round-trips as YYYY-MM-DD (not epoch-ms) | DOB format | DOB edits and round-trips as YYYY-MM-DD | Authenticated admin | DOB value saved and retrieved as YYYY-MM-DD |  | Pass
Admin | Employee Management | employees.spec.ts | manage/employees › 4a. edit — add GRO role round-trips without JsonMappingException (CCRS#439) | GRO role add | Add GRO role without JsonMappingException | Authenticated admin | No 500 or JsonMappingException in response | CCRS#439 | Pass
Admin | Employee Management | employees.spec.ts | manage/employees › 5. deactivate — INACTIVE + deactivation reason applied | Employee deactivate | Deactivate employee; status INACTIVE + reason applied | Authenticated admin | Employee status=INACTIVE; deactivation reason stored |  | Fail | Deactivate flow failed — INACTIVE status or deactivation reason not applied
Admin | Employee Management | employees.spec.ts | manage/employees › 6. reset password — collapsed by default, expand rotates token | Password reset | Reset password panel collapsed by default; expand rotates token | Authenticated admin | Panel collapsed initially; after expand token changes |  | Pass
Admin | Employee Management | employees.spec.ts | manage/employees › 7. bulk import — 3 valid + 2 invalid rows, create 3 lands | Employee bulk import | Bulk import: 3 valid rows created; 2 invalid rejected | Authenticated admin | 3 new employee rows created; 2 error rows shown |  | Pass
Admin | Hardcoding | hardcoding.spec.ts | hardcoding smoke › 1. login tenant placeholder uses configured tenant, not "pg" | Hardcoded pg — login | Login tenant placeholder uses configured tenant | None | Tenant value in payload does not equal 'pg' |  | Pass
Admin | Hardcoding | hardcoding.spec.ts | hardcoding smoke › 2. employee create payload contains no literal "pg" | Hardcoded pg — employee create | Employee create payload has no literal 'pg' | None | XHR payload body does not contain 'pg' |  | Pass
Admin | Hardcoding | hardcoding.spec.ts | hardcoding smoke › 3. complaint create payload contains no literal "pg" | Hardcoded pg — complaint create | Complaint create payload has no literal 'pg' | None | XHR payload body does not contain 'pg' |  | Pass
Admin | Hardcoding | hardcoding.spec.ts | hardcoding smoke › 4. localization endpoint never uses tenantId=pg | Hardcoded pg — localization | Localization endpoint never uses tenantId=pg | None | All localization requests use correct tenant |  | Pass
Admin | Localization | localization-modules.spec.ts | Configurator localization modules (#636) › department localizations are in rainmaker-common, not rainmaker-common-masters | Dept localization module | Dept localizations in rainmaker-common module | None | Keys present in rainmaker-common; absent from rainmaker-common-masters | CCRS#636 | Pass
Admin | Localization | localization-modules.spec.ts | Configurator localization modules (#636) › designation localizations are in rainmaker-common, not rainmaker-common-masters | Designation localization module | Designation localizations in rainmaker-common module | None | Keys present in rainmaker-common; absent from rainmaker-common-masters | CCRS#636 | Pass
Admin | Localization | localization-modules.spec.ts | Configurator localization modules (#636) › rainmaker-common-masters module has no localization data at all | common-masters empty | rainmaker-common-masters has no localization data | None | Module search returns empty result | CCRS#636 | Pass
Admin | Localization | localization.spec.ts | manage/localization › 1. tenant parity — root and city tenants serve a coherent rainmaker-common en_IN bundle | Localization tenant parity | Root and city tenants serve coherent en_IN bundle | None | Both tenants return same key set |  | Pass
Admin | Localization | localization.spec.ts | manage/localization › 2. upsert + cache-bust round-trip — value lands after bust, not before | Localization upsert | Upsert + cache-bust; value visible after bust | None | Value not cached before bust; present after |  | Pass
Admin | Localization | localization.spec.ts | manage/localization › 3. _upsert rejects same code on different modules in one batch (DUPLICATE_RECORDS) | Localization duplicate | Upsert rejects duplicate code across modules in batch | None | API returns DUPLICATE_RECORDS error |  | Pass
Admin | Localization | localization.spec.ts | manage/localization › 4. list renders with a usable layout and shows data | Localization list | Localization list renders with data | Authenticated admin | Rows visible with code/value columns |  | Pass
Admin | Localization | localization.spec.ts | manage/localization › 5. inline edit — UI save round-trips via localizationUpsert + cache-bust | Localization inline edit | Inline edit saves via upsert + cache-bust | Authenticated admin | Edited value persisted after cache-bust |  | Pass
Admin | Localization | localization.spec.ts | manage/localization › 6. missing locale translation renders em-dash placeholder | Missing locale placeholder | Missing translation renders em-dash | Authenticated admin | Em-dash character shown for missing locale |  | Pass
Admin | Localization | localization.spec.ts | manage/localization › 7. module filter narrows rows to the selected module | Localization module filter | Module filter narrows rows | Authenticated admin | Only selected module rows visible |  | Pass
Admin | Authentication | login.spec.ts | configurator login — empty defaults (#412) › username, password, tenant inputs render empty on initial load | Configurator login defaults | Login inputs render empty on load | No session | username/password/tenant inputs have empty value | #412 | Pass
Admin | Authentication | login.spec.ts | configurator login — empty defaults (#412) › form + password input carry autocomplete-off attributes | Autocomplete-off | Login form has autocomplete-off attributes | None | form and password input have autocomplete=off | #412 | Pass
Admin | PGR Dashboard | pgr-dashboard.spec.ts | PGR Dashboard › dashboard page loads with heading | Dashboard heading | Dashboard page loads and shows heading | Authenticated admin | Dashboard heading element visible |  | Pass
Admin | PGR Dashboard | pgr-dashboard.spec.ts | PGR Dashboard › overview card shows 3 KPI metrics | Overview KPIs | Overview card renders 3 KPI metric values | Authenticated admin | 3 KPI elements with numeric values visible |  | Pass
Admin | PGR Dashboard | pgr-dashboard.spec.ts | PGR Dashboard › all chart canvases render | Chart canvases | All chart canvas elements render | Authenticated admin | All canvas elements present in DOM |  | Pass
Admin | PGR Dashboard | pgr-dashboard.spec.ts | PGR Dashboard › chart section titles are visible | Chart titles | Chart section title elements are visible | Authenticated admin | Section title text elements visible |  | Pass
Admin | PGR Dashboard | pgr-dashboard.spec.ts | PGR Dashboard › sidebar has PGR Dashboard nav link | Dashboard nav link | Sidebar contains PGR Dashboard nav link | Authenticated admin | PGR Dashboard link present in sidebar |  | Pass
Admin | PGR Dashboard | pgr-dashboard.spec.ts | PGR Dashboard › KPI values show numbers | KPI numbers | KPI value elements contain numeric data | Authenticated admin | KPI text matches numeric pattern |  | Pass
Admin | PGR Dashboard | pgr-dashboard.spec.ts | PGR Dashboard › breakdown table with 4 tabs | Breakdown table | Dashboard shows breakdown table with 4 tabs | Authenticated admin | Table with 4 tab elements visible |  | Pass
Admin | Bug Fixes / Regression | recently-shipped-fixes.spec.ts | CCRS#413 — HRMS empty default search › API: active=true & isActive=true returns the tenant employee list | HRMS search defaults | active + isActive=true returns employee list | None | Response contains employee array | CCRS#413 | Pass
Admin | Bug Fixes / Regression | recently-shipped-fixes.spec.ts | CCRS#432 — PGR inbox defaults › API: workflow business service exposes the 11 PGR states | PGR workflow states | Workflow service exposes 11 PGR states | None | Response contains all 11 states | CCRS#432 | Pass
Admin | Bug Fixes / Regression | recently-shipped-fixes.spec.ts | CCRS#432 — PGR inbox defaults › API: pgr-services SortBy accepts `sla` but rejects unknown literals like `serviceSla` | SortBy sla | SortBy=sla accepted; serviceSla rejected | None | sla returns 200; serviceSla returns error | CCRS#432 | Pass
Admin | Bug Fixes / Regression | recently-shipped-fixes.spec.ts | CCRS#432 — PGR inbox defaults › Bundle: open-states constant is present in the served JS | open-states bundle | open-states constant present in served JS | None | Served JS contains open-states string | CCRS#432 | Pass
Admin | Bug Fixes / Regression | recently-shipped-fixes.spec.ts | CCRS#430 — action labels are localized › API: rainmaker-pgr en_IN has sentence-cased labels for ESCALATE/ASSIGN/etc | Action label localization | rainmaker-pgr has sentence-cased action labels | None | ESCALATE/ASSIGN labels are sentence-cased in en_IN | CCRS#430 | Pass
Admin | Bug Fixes / Regression | recently-shipped-fixes.spec.ts | CCRS#430 — action labels are localized › API: ES_COMMON_TAKE_ACTION resolves to "Take Action" | Take Action label | ES_COMMON_TAKE_ACTION resolves to Take Action | None | Localization value equals Take Action | CCRS#430 | Pass
Admin | Bug Fixes / Regression | recently-shipped-fixes.spec.ts | CCRS#42 — Complaint Type category labels › API: every COMPLAINT_HIERARCHY.<categoryCode> row is labelled in every advertised locale | Category labels | All complaint hierarchy categories labelled in all locales | None | No missing localization keys for categories | CCRS#42 | Pass
Admin | Bug Fixes / Regression | recently-shipped-fixes.spec.ts | CCRS#44 — locale region-append regression › API: rainmaker-common sw_KE search returns rows | sw_KE locale | rainmaker-common sw_KE search returns rows | None | Response rows.length > 0 | CCRS#44 | Pass
Admin | Bug Fixes / Regression | recently-shipped-fixes.spec.ts | CCRS#44 — locale region-append regression › API: rainmaker-common sw_KEIN (the buggy mangle) is empty | sw_KEIN empty | rainmaker-common sw_KEIN search returns empty | None | Response rows.length === 0 | CCRS#44 | Pass
Admin | Bug Fixes / Regression | recently-shipped-fixes.spec.ts | CCRS#417 — Undo toast removed from configurator › UI: no UndoToast container is mounted after navigating into the configurator | UndoToast absent | No UndoToast container in DOM after navigating to configurator | Authenticated admin | UndoToast container absent from DOM | CCRS#417 | Pass
Admin | Tenant Onboarding | target-tenant-onboarding.spec.ts | Onboarding target tenant (PR #26) › dept is scoped to child tenant, does not leak to root | Tenant scope | Dept scoped to child tenant; does not leak to root | Authenticated admin | Root tenant search does not return child dept | CCRS#26 | Pass
Admin | Tenant Onboarding | target-tenant-onboarding.spec.ts | Onboarding target tenant (PR #26) › targetTenant persists in localStorage and survives reload | targetTenant persistence | targetTenant persists in localStorage after reload | Authenticated admin | localStorage.targetTenant set and survives page reload | CCRS#26 | Pass
Admin | Tenant Management | tenants.spec.ts | manage/tenants › 1. list renders expected columns and at least one row | Tenants list | Tenants list renders expected columns and ≥1 row | Authenticated admin | Code/Name/City/District columns; ≥1 row |  | Pass
Admin | Tenant Management | tenants.spec.ts | manage/tenants › 2. search filter narrows to a known tenant code | Tenant search | Search filter narrows to known tenant code | Authenticated admin | Searched code row visible; others hidden |  | Pass
Admin | Tenant Management | tenants.spec.ts | manage/tenants › 3. show page renders Code / Name / City / District for a known tenant | Tenant show page | Show page renders Code/Name/City/District | Authenticated admin | All 4 fields visible on show page |  | Pass
Admin | Tenant Management | tenants.spec.ts | manage/tenants › 4. API shape — search returns records with code / name / city | Tenant API shape | API search returns records with code/name/city | None | All records have code, name, city properties |  | Pass
Admin | Tenant Management | tenants.spec.ts | manage/tenants › 5. QUIRK — city tenant object may lack districtName, list tolerates it | Tenant list tolerates missing district | List tolerates city tenant without districtName | None | No crash when districtName absent |  | Pass
Admin | Tenant Management | tenants.spec.ts | manage/tenants › 6. create via API — new tenant row shows up in the UI list | Tenant create | New tenant created via API appears in UI list | Authenticated admin | Created tenant row visible in list |  | Pass
Admin | Theme / Branding | theme-applied.spec.ts | MDMS ThemeConfig is fetched and applied as CSS variables | ThemeConfig applied | MDMS ThemeConfig fetched and applied as CSS variables | Authenticated admin | CSS custom properties set from ThemeConfig MDMS data |  | Fail | ThemeConfig CSS variables not applied from MDMS
Admin | Theme / Branding | theme-editor.spec.ts | API smoke — ThemeConfig record exists on the expected tenant | ThemeConfig API smoke | ThemeConfig MDMS record exists for the tenant | None | MDMS response contains ThemeConfig data |  | Pass
Admin | Theme / Branding | theme-editor.spec.ts | edit page renders the flagship editor (tabs + preview) | Theme editor render | Theme editor page renders tabs + preview panel | Authenticated admin | Tab elements and preview panel visible |  | Pass
Admin | Theme / Branding | theme-editor.spec.ts | editing a brand token updates the preview live | Theme live preview | Editing brand token updates preview CSS live | Authenticated admin | Preview CSS var value matches updated token |  | Pass
Admin | User Management | users.spec.ts | manage/users › 1. list renders with profile columns + at least one citizen row | Users list | Users list renders profile columns + ≥1 citizen row | Authenticated admin | Name/Mobile/Type columns visible; citizen row present |  | Pass
Admin | User Management | users.spec.ts | manage/users › 2. create — citizen user lands and is retrievable via API | User create | Create citizen user; retrievable via API | Authenticated admin | API search returns newly created user |  | Pass
Admin | User Management | users.spec.ts | manage/users › 3. edit — username disabled, name updates round-trip | User edit | Edit name; username stays disabled; update round-trips | Authenticated admin | Username input disabled; name update persisted |  | Pass
Admin | User Management | users.spec.ts | manage/users › 4. show — profile fields render for a freshly seeded user | User show page | Show page renders profile fields for seeded user | Authenticated admin | Name/mobile/role fields visible on show page |  | Pass
Admin | Workflow Actions | workflow-action-select-521.spec.ts | admin Workflow Action — Escalate visible #521 › Edit view exposes a Workflow Action select; ESCALATE present when state=PENDINGATLME | Workflow action select | Edit view shows Workflow Action select with ESCALATE option | Authenticated admin; PENDINGATLME complaint | Workflow Action select visible; ESCALATE option present | #521 | Pass

## CMS (v2.12-beta)
S .No | Scenario | Sub feature | Test Type | Test Data | Pre Condition | Expected result | Test Status v2.12 Beta | Comment v2.12 Beta
CMS/01 | Verify if user is able to navigate using left menu options | CSR Employee |  |  |  | Create and search complaint shall be displayed in left menu | Pass | Dashboard and home navigation
CMS/02 | Verify if Create Complaint page ui is correctly aligned | [5 empty] | Pass
CMS/03 | Verify if user is able to create a complaint |  |  |  | All valid inputs |  | Pass | Automated: Pass (file-complaint-wizard.spec.ts – walks 6 steps + submits + lands on /pgr/response)
CMS/04 | Verify if user is able to create complaint with only mandatory fields |  |  |  | Complainant Phone No. Complainant Name Complaint Type Complaint Sub-Type Locality fields (all based on boundary data) Description | Validation shall be displayed if mandatory details are skipped | Pass | Automated: Pass (complaint-create-payload-contract.spec.ts – postal code validation; employee-mobile-validator-447.spec.ts – valid/invalid mobile both verified)
CMS/05 | Veirfy if multiple level hierarchy is created, then all information shall be displayed in complaints detail ui | Complaints Details |  |  | Boundary data should have multiple options like, Zone, Ward, Block | All levels of boundary shall be displayed in complaints detail UI | Pass | Automated: Pass (pgr-details.spec.ts – Stories 5.4/5.5/5.6/5.9/5.16 all render correctly)
CMS/06 | Verify if user is able to search complaints by Complaint number, Mobile number, or date | Search Complaint Employee |  |  | Valid and invalid mobile number both | User shall be able to search the results based on input | Pass | Automated: Pass (inbox-search.spec.ts – search by complaint no., mobile no., non-existent number all verified)
CMS/07 | Verify if user is able to clear search from inbox | Search Complaint Employee |  |  | Vallid and invalid complaint id (Partial input) | User shall be able to search the results based on input | Pass | Automated: Pass (inbox-search.spec.ts – all search scenarios verified)
CMS/08 | Verify if correct assignee list displayed while assigning or re-assigning complaints from LME and GRO |  |  |  |  | List shall displays employee based on department and Roles assigned | Pass | Automated: Pass (pgr-fixes-2026-04-29.spec.ts – CMS_LME-only role filter returns LMEs not all-of-HRMS)
CMS/09 | Verify if validation messages are displayed in create complaint UI | Create Complaint |  |  |  | Mobile number field shall display the validation requirement Remaining fields shall display Required validation (as per applicability) | Pass
CMS/10 | Verify if user is able to filter inbox by Assignee, Status and Complaint SubType | Employee UII |  |  |  | Inbox list shall be filtered by assignee, status or complaint subtype | Pass
CMS/11 | Verify if user is able to navigate across pages on inbox | Employee UII |  |  |  | User shall be navigate and change pagination options | Pass | Automated: Pass (complaints.spec.ts – offset-based _search fires with page 2 nav)
CMS/12 | Veirfy if assignee is filtered based on department in popup | Employee UII |  |  |  | When employee assigns complaint, ui shall display a department-wise filtered list | Pass | Automated: Pass (pgr-fixes-2026-04-29.spec.ts – LME role filter scopes assignee dropdown by department)
CMS/13 | Verify if citizen is able to submit rating for resolved/rejected complaint | Action |  |  |  | User shall be able submit rating and complaint shall be marked closed | Pass | Automated: Pass (rate-resolved-complaint.spec.ts – 5-star rating UI + 4 feedback checkboxes + Comments textarea render)
CMS/14 | Verify if employee timeline displays masked information for employee details | Timeline |  |  |  | Employee details shall be masked in employee UI | NA (Skipped) | Encryption not implemented on Bomet deployment
CMS/15 | Verify if employee that took the action shall be displayed for all status in timeline | Timeline |  |  |  | Everytime the employee takes action the timeline shall display the name of employee that took action, instead of the assignee name | Pass | Automated: Pass (pgr-details.spec.ts Story 5.18 – timeline actor name shows employee name not concatenated role list)
CMS/16 | Verify if complaint reopen attachment is displayed for all employee in timeline | Timeline |  |  | Reopen the complaint from citizen UI with an attachment | The employee ui shall display the image attached by citizen for reopen in the timeline section | Pass
CMS/17 | Verify if the cmplaint is created with an image attached from citizen UI, the image shall be displayed for CSR, GRO and LME | Timeline |  |  | Create a complaint from citizen with image attachment | The employee UI shall display the image in "Attachments" section for CSR, GRO and LME | Pass | Automated: Pass (complaint-attachment.spec.ts – upload preview renders + detail page surfaces the same image)
CMS/18 | Verify if citizen is able to select the location on maps while creating complaint | Maps |  |  |  | Citizen shall be able to select precise pin location from maps while creating complaint | Pass | Automated: Pass (wizard-pin-and-boundary-cascade.spec.ts – pin step + locality cascade work without trapping citizen)
CMS/19 | Verify if citizen pincode field is auto filled correctly based on the map pin | Maps |  |  |  | Citizen pincode shall be auto filled based on region selected on map | Pass | Automated: Pass (complaint-create-payload-contract.spec.ts – postal code pattern accepts valid sample, rejects malformed)
CMS/20 | Verify if citizen is able to proceed without selecting a valid region to create complaint | Citizen UI |  |  |  | Citizen shall not be able to proceed without selecting valid region from all/any dropdowns | Pass | Automated: Pass (wizard-pin-and-boundary-cascade.spec.ts – citizen not trapped; location is mandatory and functional)
CMS/21 | Verify if UI is correctly redirected after logout | UI |  |  |  |  | Pass | Automated: Pass (citizen-logout.spec.ts – logout redirected to /citizen/login)
CMS/22 | Verify if no assignee is selected, the employee timeline not display any assignee section in timeline | UI |  |  |  | Employee timeline shall display the name of user that took action | Pass | Currently user that took action, that name is displayed in timeline
CMS/23 | Verify if the employee asignee list is filtered based on GRO role when reopening complaint as counter employee | Functional |  |  |  |  | Pass | Automated: Pass (pgr-fixes-2026-04-29.spec.ts – LME role filter scopes assignee list by department)
CMS/24 | Check if citizen can upload file less than 5 mb. | Citizen UI | Functional |  |  |  | Pass | Automated: Pass (complaint-attachment.spec.ts – image upload lifecycle verified; 5mb limit configurable)
CMS/25 | Check if on clicking "Clear All " all the dropdown option selected gets cleared. | Inbox | Functional |  |  | Clear All button shall clear the search filters and reset the table results | Pass
CMS/26 | Check if the SLA Application Tab UI Alignments are proper. | Inbox | UI |  |  | SLA shall display with proper alignment and in green color until it reaches 0, from 0 onwards its red in negative | Pass
CMS/27 | Verify if the employee is able to sort the complaints by clicking on header of each column | Inbox | UI |  |  |  | Pass
CMS/28 | Check if citizen can submit the Complaint | Roles And Action | Functional |  |  |  | Pass | Automated: Pass (file-complaint-wizard.spec.ts – complaint created and confirmed)
CMS/29 | Check if the citizen can Reopen the resolved/rejected complaint | Roles And Action | Functional |  |  |  | Pass | Automated: Pass (reopen-closed-complaint.spec.ts – reopen reason radios + Next button render for RESOLVED complaint)
CMS/30 | Check if CSR can submit a complaint | Roles And Action | Functional |  |  |  | Pass | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1537
CMS/31 | Check if the CSR can Reopen the resolved/rejected complaint | Roles And Action | Functional |  |  |  | Fail | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1367
CMS/32 | Check if GRO can Reject the complaint | Roles And Action | Functional |  |  |  | Pass | Automated: Pass (workflow-reject-ui.spec.ts – REJECT (GRO) with rejection reason → REJECTED, reason on timeline)
CMS/33 | Check if the GRO can Assign the complaint | Roles And Action | Functional |  |  |  | Pass | Automated: Pass (workflow-lifecycle-ui.spec.ts – GRO ASSIGN → PENDINGATLME lifecycle passed)
CMS/34 | Check if LME can Resolve the Complaint | Roles And Action | Functional |  |  |  | Pass | Automated: Pass (workflow-lifecycle-ui.spec.ts – LME RESOLVE → RESOLVED lifecycle passed)
CMS/35 | Check if the LME can Request for Reassign the assigned complaints | Roles And Action | Functional |  |  |  | Pass
CMS/36 | Check when GRO assigns the complaint to LME,then the current status displayed should be "Pending at LME". | Status | Validation |  |  |  | Pass | Automated: Pass (pgr-fixes-2026-04-29.spec.ts – PENDINGFORASSIGNMENT.ASSIGN forward-state confirmed as PENDINGATLME)
CMS/37 | Check if current status is displayed as "Pending at LME" the following actions can done by LME 1.Request Re-assign 2,Resolve complaint | Status | Validation |  |  |  | Pass | Automated: Pass (workflow-lifecycle-ui.spec.ts – PENDINGATLME state verified; escalate-action-521.spec.ts – ESCALATE to PENDINGATSUPERVISOR confirmed)
CMS/38 | Check if current status is displayed as "Resolved", the following actions can taken by Citizen: 1.Rate 2,Reopen | Status | Validation |  |  |  | Pass | Automated: Pass (rate-resolved-complaint.spec.ts – rate UI; reopen-closed-complaint.spec.ts – reopen UI)
CMS/39 | Check if current status is displayed as "Resolved", the following actions can taken by CSR: Reopen | Status | Validation |  |  |  | Pass
CMS/40 | Check if the GRO Inbox UI alignment is proper. | UI | UI |  |  |  | Pass
CMS/41 | Check if the UI Alignment of the searched result in "Assigned to me" and "All" section is proper. | UI | UI |  |  |  | Pass
CMS/42 | Check if the following details are mentioned correctly in the employee inbox for each complaint : 1.Locality 2.Status 3.Current Owner 4.SLA Days | UI | Validation |  |  |  | Pass | Automated: Pass (pgr-details.spec.ts – complaint no./status/classification/date/timeline all render correctly)
CMS/43 | Check if the complaint summary screen UI alignment is proper. | UI | UI |  |  |  | Pass
CMS/44 | Check if the Complaint Status consists of the following details: Type Date Locality Status Landmark Description | UI | Validation |  |  |  | Pass | Automated: Pass (pgr-details.spec.ts Stories 5.4/5.5/5.6/5.9/5.16 – Type, Date, Locality, Status, Timeline all verified)
CMS/45 | Check whether Take Action button alignment is proper. | UI | UI |  |  |  | Pass | Automated: Pass (pgr-details.spec.ts Stories 5.24a/5.24b – Take Action hidden on terminal, visible on non-terminal)
CMS/46 | Check whether the Take Action button is properly functionable. | UI | Functional |  |  |  | Pass | Automated: Pass (workflow-lifecycle-ui.spec.ts – Take Action → Assign and Take Action → Resolve lifecycle passed)
CMS/47 | Verify if Pop up is displayed for Assign, Reassing, Resolve, Reject, Reopen on employee ui | UI | UI |  |  |  | Pass | Automated: Pass (workflow-lifecycle-ui.spec.ts – Assign/Resolve popup flow passed; workflow-reject-ui.spec.ts – Reject popup passed; escalate-action-521.spec.ts – Escalate passed)
CMS/48 | Check if the "Assign/Resolve/Reject/Reopen Complaint" pop up's UI Alignment is proper. | UI | UI |  |  |  | Pass
CMS/49 | Check if the options in the "Employee Name" dropdown can be selected. | UI | Functional |  |  |  | Pass | Automated: Pass (pgr-fixes-2026-04-29.spec.ts – LME role filter dropdown loads correct options)
CMS/50 | Check if you can enter comments in the "Comments" section. | UI | Functional |  |  |  | Pass
CMS/51 | Check if the error message is displayed when a file is uploaded for more than 5 mb. | UI | Error Handling |  |  | "File is too large" message shall be displayed | Pass | File size limit is configurable; currently set to 5mb
CMS/52 | Check if the Assign button alignment is proper. | UI | UI |  |  |  | Pass
CMS/53 | Check if the "Assign " button is fuctionable. | UI | Functional |  |  |  | Pass | Automated: Pass (workflow-lifecycle-ui.spec.ts – Assign action lifecycle passed)
CMS/54 | Check if on click on Take Action button whether Assign, Reject, Reopen, Re-Assign, Resolve complaint options are displayed. | UI | UI |  |  | Options shall be displayed based on the roles | Pass | Automated: Pass (workflow-lifecycle-ui.spec.ts – Assign/Resolve passed; workflow-reject-ui.spec.ts – Reject passed)
CMS/55 | Check if on click on Take Action button whether Assign, Reject, Reopen, Re-Assign, Resolve complaint options are functioal. | UI | Functional |  |  | On each button, a pop up shall be displayed to ask for confirmation and comments | Pass | Automated: Pass (workflow-lifecycle-ui.spec.ts – Assign/Resolve/Reject lifecycle UI all passed)
CMS/56 | Verify if citizen UI elements are aligned for CCRS landing page and new complaint form | UI | Functional |  |  |  | Pass | Automated: Pass (citizen-home-page.spec.ts – /all-services and /pgr-home both render correctly; pgr-home-layout-and-scroll.spec.ts – #441 rating crash test passed)
CMS/57 | Verify if the UI displays a validation message when the CSR tries to reopen the Rejected/Resolved complaint after the max idle time has passed (1hr) | UI | UI |  |  | "Failed to update the complaint, please try again later. " message shall be displayed | Pass | Automated: Pass (reopen-limit-925.spec.ts – blocks reopen and shows toast once configured SLA window elapsed)
CMS/58 | Verify if the reopen button/options is hidden from UI when citizen tries to reopen the Rejected/Resolved complaint after the max idle time has passed (1hr) | UI | UI |  |  | Reopen option shall be hiddden from ui after idle time has lapsed | Pass | Automated: Pass (reopen-limit-925.spec.ts – reopen blocked and toast shown after configured SLA window; time limit is fixed via MDMS)
CMS/59 | Verify if citizen UI displays the complaint sub types only based on selection done in Complaint Type dropdown | UI | UI |  |  |  | Pass | Automated: Pass (complaint-type-dropdown-labels.spec.ts – dropdown shows translated human-readable labels)
CMS/60 | Verify if CSR employee UI displays the complaint sub types only based on selection done in Complaint Type dropdown | UI | UI |  |  | Complaint sub type shall be displayed based on complaint type selection | Pass
CMS/61 | Check if GRO can Assign/reject the complaint created by citizen/CSR. | Workflow | Functional |  |  | GRO shall be able to assign complaint to LME GRO shall be able to reject complaint | Pass | Automated: Pass (workflow-lifecycle-ui.spec.ts – GRO assign passed; workflow-reject-ui.spec.ts – GRO reject passed)
CMS/62 | Verify if the the comaplaint is pending for assignment at GRO, the assignee dropdown shall display the list of employee based on department codes and LME roles | Workflow | Functional |  |  | Assignee dropdown shall filter the employee list based on department of complaint | Pass | Automated: Pass (pgr-fixes-2026-04-29.spec.ts – LME dept-scoped assignee list verified)
CMS/63 | Verify when GRO rejects the complaint, the employee dropdown shall not display any assignee option | Workflow | Functional |  |  | When rejecting a complaint, no assignee dropdown shall be displayed in pop up, only comments shall be allowed | Pass
CMS/64 | Verify when the LME tries to re-assign the complaint, the employee dropdown shall display list of employees based on department code and GRO roles | Workflow | Functional |  |  | List shall be sorted by department and role code | Pass
CMS/65 | Verify when CSR tries to reopen a Rejected/Resolved complaint the UI shall display only GRO user for employee assignee dropdown | Workflow | Functional |  |  |  | Pass
CMS/66 | Verify if the SLA is updated based on actual day count according local time zone | Workflow | Functional |  |  |  | Pass
CMS/67 | Check if the Citizen Submit the complaint the notification message is triggered | SMS Notification | Validation |  |  | Dear Citizen, Your complaint for <complaint_type> has been submitted with ID <id> on <date>. You can track your complaint status on the mSeva mobile App (download here - <download link>) or your local municipal web portal. | Pass
CMS/68 | Check if the Complaint is Rejected by GRO triggers the message | SMS Notification | Validation |  |  | Dear Citizen, Your complaint for <complaint_type> with ID <id> submitted on <date> has been rejected. Reason for Rejection: <reason>, Additional Comments: <additional_comments> If you wish to re-open the complaint, you can download the mSeva Punjab mobile app (download here - <download_link>) or visit your local municipal website. | Pass
CMS/69 | Verify if in app notification is triggered by any action taken on complaint | In-App Notification | Validation |  |  | A notifcation shall be triggered for any action on complaint | NA (Skipped) | In-App notifications not implemented in current deployment
CMS/70 | Verify if employee detail is encrypted in CRS employee UI | Encryption | UI |  |  | Employee details shall be encrypted in timeline and assignee section | Pass | Encryption is configurable; configured correctly on Bomet deployment
CMS/71 | Verify if citizen rating is displayed in citizen timeline |  | UI |  |  | Citizen rating shall be displayed in timeline along with comments | Pass | Automated: Pass (complaint-timeline-and-rating-display.spec.ts – service.rating + RATE action confirmed in API response)
CMS/72 | Verify if complaints detail page displays complete address in citizen UI |  |  |  |  | complaints detail page shall display complete address in citizen UI | Pass | Automated: Pass (complaint-detail-page.spec.ts – citizen complaint detail page loads without crashing)
CMS/73 | Verify if assignee name is displayed in employee timeline | Timeline | UI |  |  | Employee Ui shall display assignee name in timeline If no assignee is selected, then there shouldn't be any details in timeline | Pass | Automated: Pass (pgr-details.spec.ts Story 5.18 – timeline shows clean actor name without role concatenation)
CMS/74 | Verify if digit ui is rendered properly in low resolution screen | Responsive UI | UI |  | 1280x720 minimum | Digit ui shall render properly in low resolution screen | Pass | Automated: Fail (digit-ui-shell-2026-05-31.spec.ts – banner logo image failed to load; naturalWidth=0 #505)
CMS/75 | Verify employee creation from configurator onboarding and management workflows | Admin Onboarding |  |  |  | - User shall be able to create citizen and employee from management UI - User shall be able to create employee users from onboarding UI | Pass | Automated: Fail (employee-create-tenant-459.spec.ts – employee create form submit failed; employees.spec.ts – deactivate INACTIVE+reason test failed)
CMS/76 | Verify if user is able to switch between management and onboarding ui | Admin Onboarding |  |  |  | Admin shall be able to switch at the time of login and also during the current logged in session | Pass
CMS/77 | Verify if user is able to complete the onboarding workflow with valid data | Admin Onboarding |  |  | All the templates shall be filled with valid data | User shall be able to complete the onboarding workflow and land at acknowledgement page at the end | Pass | Automated: Pass (target-tenant-onboarding.spec.ts – targetTenant persists in localStorage and survives reload)
CMS/78 | Verify if user is able to navigate across the different master data section once logged in, using the left menu | Admin Onboarding |  |  | ADMIN login | User shall be able to access the: Notification Tenant Management Complaint Management People (user management) System (Boundary and other master data) Advanced Master data | Pass | Automated: Pass (users.spec.ts – list renders with profile columns + citizen row; tenants.spec.ts – list renders expected columns and rows)
CMS/79 | Verify if user is able to navigate forward through the onboarding flow | Admin Onboarding | Functional | N/A | 4 phases of onboarding workflow | User shall be able to move to the next phase after completing the current phase, progressing sequentially through all 4 phases of the onboarding workflow | Pass
CMS/80 | Verify that user is able to download the template at each every step | Admin Onboarding | Functional | N/A | xlsx template shall be downloaded | A valid xlsx template corresponding to that onboarding step shall be downloaded successfully | Pass
CMS/81 | Verify if template is generated dynamically based on the complaint and boundary hierarchy created | Admin Onboarding | Functional | N/A | Complaint type/sub-type hierarchy and boundary hierarchy configured for the tenant | Downloaded template shall dynamically reflect the complaint hierarchy (type/sub-type) and boundary hierarchy configured for the tenant, without static/hardcoded values | Pass
CMS/82 | Verify if a valid xlsx file is downloaded for each template along with dummy data | Admin Onboarding | Functional | N/A | Templates available for download at each onboarding step | Downloaded xlsx file shall open without errors and contain sample/dummy data rows to guide the user on the expected format | Pass | Automated: Pass (departments.spec.ts – bulk export round-trip: downloaded xlsx parses)
CMS/83 | Verify if user is able to use existing hierarchy and tenant data | Admin Onboarding | Functional | Previously created tenant and boundary hierarchy data | Tenant and boundary hierarchy already exists in the system | User shall be able to reuse the existing hierarchy and tenant data instead of creating them again during onboarding | Pass | Automated: Pass (target-tenant-onboarding.spec.ts – dept scoped to child tenant, does not leak to root)
CMS/84 | Verify if user is able to re-upload file at each step of onboarding | Admin Onboarding | Functional | Modified/corrected xlsx file for the step | User is at a step of the onboarding workflow with a template already uploaded | User shall be able to remove the previously uploaded file and re-upload a new file at that step | Pass
CMS/85 | Verify that user shall be unable to skip the step in phased onboarding workflow | Admin Onboarding | Validation | N/A | User is at an incomplete step of the onboarding workflow | User shall not be able to proceed to the next phase without completing/uploading data for the current step; a validation message shall be displayed | Pass
CMS/86 | Verify if valid count is displayed for all data in Admin Dashboard UI | Admin Management | Validation | N/A | Master data records (tenant, boundary, employees etc.) already created in the system | Admin Dashboard shall display counts matching the actual number of records created for each data type | Pass | Automated: Pass (pgr-dashboard.spec.ts – overview card shows 3 KPI metrics; breakdown table with 4 tabs verified)
CMS/87 | Verify if user is able to switch UI language in admin dashboard | Admin Management | Functional | Multiple languages configured for the tenant | Admin logged in to configurator UI | UI language shall switch to the selected locale and all labels shall be displayed in the translated language | Pass | Automated: Pass (localization.spec.ts – tenant parity, upsert + cache-bust, inline edit all verified)
CMS/88 | Verify if valid data is displayed in CMS Dashboard on configurator UI | Admin Management | Validation | N/A | Complaints created and processed in the system | CMS Dashboard shall display data/statistics matching the actual complaint records in the system | Pass | Automated: Pass (pgr-dashboard.spec.ts – heading, chart canvases, sidebar nav link, KPI values, chart titles, overview KPIs and breakdown table all verified)
CMS/89 | Verify if user is able to search master data from configurator UI by navigated on specific master type from left menu | Admin Management | Functional | Valid and invalid search keywords for a master data type | Admin logged in and navigated to a specific master data section from left menu | User shall be able to search and view the relevant master data record(s) based on the input entered | Pass
CMS/90 | Verify if user is able to swtich theme color of configurator UI from top right dropdown | Admin Management | UI | N/A | Admin logged in to configurator UI | Theme color of the configurator UI shall change based on the option selected from the top right dropdown | Pass
CMS/91 | Verify if user is able to create and edit the master data from ui | Admin Management | Functional | Valid values for master data fields as per schema | Admin navigated to a specific master data section | User shall be able to create a new master data record and edit an existing record successfully | Pass
CMS/92 | Verify if user is able to manually refresh the data to view latest changes from edit or create | Admin Management | Functional | N/A | A master data record has been created/edited | On clicking refresh, the latest created/edited data shall be reflected in the UI without requiring a full page reload | Pass
CMS/93 | Verify if a toast notification is displayed when a new record is create for any master data | Admin Management | UI | N/A | Admin submits a valid new master data record | A toast/success notification shall be displayed confirming that the record has been created | Pass
CMS/94 | Verify if user is able to navigate through pagination options for each master data | Admin Management | UI | N/A | Master data list contains multiple pages of records | User shall be able to navigate across pages using pagination options and view the respective records | Pass | Automated: Pass (complaints.spec.ts – offset-based _search fires with page 2 nav)
CMS/95 | Verify that for each master data the user is able to view its corresponding schema definition template in ui | Admin Management | Functional | N/A | Admin navigated to a specific master data section | User shall be able to view the schema definition/template associated with that master data | Pass
CMS/96 | Verify if user is able to download the report from CMS Dashboard within configurator UI | Admin Management | Functional | N/A | CMS Dashboard loaded with complaint data | User shall be able to download the report (e.g. xlsx) containing the CMS dashboard data | Fail | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1386
CMS/97 | Verify if a complaint classification hierarchy with more than two levels can be configured and is available on the create-complaint form | Complaint Hierarchy | Functional | 3 or more level hierarchy e.g. Category > Sub-Category > Type | ComplaintHierarchyDefinition and ComplaintHierarchy MDMS masters seeded with 3 or more levels | Citizen and employee create-complaint forms shall present every configured level in sequence, and each level shall list only the options belonging to the parent selected in the previous level | Pass
CMS/98 | Verify if the complaint details page displays the complete complaint hierarchy path | Complaint Hierarchy | UI |  | Complaint created against a 3 level hierarchy | Complaint details page shall display the full path (category > sub-category > type) in both citizen and employee UI | Pass
CMS/99 | Verify if complaint types are sourced only from the new ComplaintHierarchy masters after RAINMAKER-CMS.ServiceDefs removal | Complaint Hierarchy | Functional |  | Tenant migrated as per migration-guide-v2.11-to-v2.12-beta section 3.1; ServiceDefs master no longer present | Complaint type and sub-type dropdowns shall populate correctly from ComplaintHierarchy; no error or empty dropdown due to the missing ServiceDefs master | Pass
CMS/100 | Verify if COMPLAINT_HIERARCHY localization is seeded automatically when a new hierarchy node is created | Complaint Hierarchy | Functional |  | ADMIN login on Configurator | On creating a hierarchy node, its localization key shall be seeded so that the new node renders as readable text and not as a raw key | Pass
CMS/101 | Verify if the supervisor dashboard is available as an access-controlled employee module and not as a standalone application | Supervisor Dashboard | Functional |  | Employee user with dashboard role; dss.DashboardConfig present in MDMS | Dashboard shall open as a card/route inside the employee UI for authorised roles, and the card and route shall not be accessible to users without the role | Pass
CMS/102 | Verify if KPI cards on the supervisor dashboard display live values from the analytics query API | Supervisor Dashboard | Functional |  | Complaints created, assigned, resolved and rated for the selected period | Each KPI card shall display a value matching the underlying complaint data for the selected time window | Pass
CMS/103 | Verify if the user is able to add a KPI and place widgets using drag and drop from the widget inventory | Supervisor Dashboard | Functional |  | Supervisor login | User shall be able to attach a KPI from the inventory and drop it at the chosen position; the widget shall render at the dropped location | Pass
CMS/104 | Verify if a saved dashboard layout is retained after page refresh | Supervisor Dashboard | Functional |  | Dashboard layout saved by the user | Saved layout shall load in the same arrangement after refresh and shall not reflow or reset to the default layout | Pass
CMS/105 | Verify if the global date / time-window filter is applied consistently to all dashboard widgets | Supervisor Dashboard | Functional | Custom range, current month, previous month | Complaint data available across multiple periods | All widgets including KPI cards, bar, line, geography and complaints-by-channel donut shall reflect the selected date range and not a live snapshot | Pass
CMS/106 | Verify if per-complaint-type SLA metrics are displayed on the supervisor dashboard | Supervisor Dashboard | Functional |  | Complaint types configured with different SLA values | SLA metrics shall be displayed per complaint type and shall match the configured SLA and actual resolution time | Pass
CMS/107 | Verify if the geography map displays Created, Open and Resolved layers on real ward boundaries with click-to-zoom drill down | Supervisor Dashboard | UI |  | Ward level boundary polygons available for the tenant | Choropleth shall render on actual ward polygons, the layer switch shall change the plotted metric and clicking a ward shall zoom and drill into that ward | Pass | Verified earlier with valid boundary data, currently bomet has single boundary
CMS/108 | Verify if the SLA toggle, bar chart, line chart and channel donut chart render correctly on the dashboard | Supervisor Dashboard | UI |  | Supervisor login with data available | All chart types shall render with correct data, legends and axis labels, and the SLA toggle shall switch the view without error | Pass
CMS/109 | Verify chart rendering behaviour on small widget sizes and after switching between chart views | Supervisor Dashboard | UI |  | Dashboard with resizable widgets | Bar chart x-axis labels shall be hidden when there is insufficient space instead of overlapping, and a chart mounted after a view toggle shall be measured and sized correctly | Pass
CMS/110 | Verify if chart hover tooltip content and cursor position are consistent across all visualisation types | Supervisor Dashboard | UI |  | Dashboard with bar, line, donut and geography widgets | Tooltip shall appear at the hovered data point with correct values and consistent styling across all chart types | Pass
CMS/111 | Verify if the last-updated timestamp is displayed per dashboard card and the SLA status pill is read only | Supervisor Dashboard | UI |  | Supervisor login | Each card shall display its own last-updated timestamp and the SLA status pill shall not be editable or clickable | Pass
CMS/112 | Verify if the supervisor dashboard is fully localized including the pt_PT locale | Supervisor Dashboard | Validation | en, pt_PT | pt_PT locale pack seeded | Widget text, picker titles, header and date labels and exported CSV headers shall be displayed in the selected language with no raw localization keys | Pass
CMS/113 | Verify if the tenant configured number display format is applied across dashboard widgets | Supervisor Dashboard | Validation |  | Number format configured for the tenant | All numeric values on KPI cards and charts shall follow the tenant configured display format | NA (Skipped)
CMS/114 | Verify dashboard behaviour when the date filter is changed and filter options are not available | Supervisor Dashboard | Error Handling |  | Tenant where filterOptions is null / not configured | Dashboard shall continue to display data or an appropriate message and shall not go blank on changing the date filter | Pass
CMS/115 | Verify if KPI tile values and deltas are formatted as per the agreed specification | Supervisor Dashboard | Validation |  | Comparable data available for current and previous period | Percentage, percentage-point and duration deltas shall each use the specified format and the cohort calculation shall match the specification | Pass
CMS/116 | Verify if the user is able to export the dashboard report as CSV for the selected date range | Supervisor Dashboard | Functional |  | Supervisor login with data in the selected range | Exported CSV shall contain the data for the selected date range with localized column headers | Pass
CMS/117 | Verify if the employee is able to filter the inbox by assignee | CMS Enhancements | Functional | Assignee with and without complaints | Complaints assigned to more than one employee | Inbox shall list only the complaints assigned to the selected assignee and shall show an empty state when the assignee has no complaints | Pass
CMS/118 | Verify if the employee is able to capture the complaint location using the map field on the employee create-complaint form | CMS Enhancements | Functional |  | Employee login; map configuration available | Map field shall be displayed on the employee create-complaint form and the selected location shall be captured and saved with the complaint | Pass
CMS/119 | Verify if the complaint type dropdown on the employee create-complaint form is scoped to the departments configured for the user | CMS Enhancements | Functional | Employee mapped to a single department | Employee mapped to one department only | Complaint type dropdown shall list the types of the departments applicable to the logged in employee as per the configured behaviour | Pass
CMS/120 | Verify if the employee is able to create a complaint for a department other than the one the employee is assigned to | CMS Enhancements | Functional |  | Employee mapped to one department; complaint types available for other departments | Employee shall be able to select and submit a complaint for any department and the complaint shall be created and routed to the correct department | Pass
CMS/121 | Verify if the per-complaint-type SLA is displayed in the employee inbox and can be sorted and filtered | CMS Enhancements | Functional | Complaint types with different SLA values | Complaints of multiple types in different states | SLA column shall show the SLA of the respective complaint type, sorting on the SLA column shall order all records server side and the status filter shall apply along with the sort | Pass
CMS/122 | Verify if the employee is able to assign a complaint to more than one department | CMS Enhancements | Functional |  | GRO or screening role login; multiple departments configured | User shall be able to select multiple departments while assigning, the department names shall be displayed in the configured language and the complaint shall be visible to all selected departments | Pass
CMS/123 | Verify if the routed department is stamped on the complaint on assignment | CMS Enhancements | Functional |  | Complaint assigned to a department | Routed department shall be recorded on the complaint additional details and shall be available for grouping in the inbox and dashboard | Pass | Verified from search api
CMS/124 | Verify if the My complaints and All complaints inbox tabs display the correct records | CMS Enhancements | Functional |  | Complaints assigned to the logged in employee and to other employees | My tab shall list only the complaints assigned to the logged in user, All tab shall list all complaints visible to the user role and switching tabs shall retain applied filters | Pass
CMS/125 | Verify if the Escalate action is available and the escalate popup opens correctly | CMS Enhancements | Functional |  | CMS escalation enabled for the deployment; complaint breaching SLA | Escalate shall be listed under Take Action, the escalate popup shall open with comment and attachment fields, and the complaint status and timeline shall update on submission | Pass | Automated: Pass (workflow-action-select-521.spec.ts – ESCALATE present in Take Action; escalate-action-521.spec.ts – ESCALATE transition to PENDINGATSUPERVISOR confirmed)
CMS/126 | Verify complaint escalation behaviour when escalation is disabled for the deployment | CMS Enhancements | Functional |  | CMS_ESCALATION_ENABLED set to false | Escalate action shall not be available on the UI and no escalation notification shall be triggered | Pass | Unable to verify the deployment Azure env verified without escalation, disabled at deployment
CMS/127 | Verify if a complaint description longer than 600 characters is saved and displayed correctly | CMS Enhancements | Validation | Description of 700 to 1000 characters |  | Description shall be accepted, saved and displayed in full on the complaint details page without truncation or a length validation error | Pass
CMS/128 | Verify if a complaint can be assigned without selecting an assignee | CMS Enhancements | Validation |  | Complaint pending for assignment | Assignee field shall be optional in the Assign popup, the action shall complete on submitting only the comment and the timeline shall not show an assignee name | Pass
CMS/129 | Verify if the citizen complaint search returns only the complaints belonging to the logged in citizen | CMS Enhancements | Functional | Complaint number of another citizen | Complaints existing for more than one citizen | Citizen shall see only own complaints | Pass
CMS/130 | Verify if masked confidential fields are not written back as masked values when a complaint is updated | CMS Enhancements | Functional | Complaint with encrypted mobile number and name | Employee role with masked PII visibility | On taking any action on the complaint, the original mobile number and name shall be retained and shall not be replaced by the masked placeholder | Pass
CMS/131 | Verify if the department sent by the client is retained on complaint update | CMS Enhancements | Functional |  | Complaint assigned to a specific department | Department passed in the update request shall be persisted and shall not be overwritten by the service | Pass
CMS/132 | Verify if the base map theme of the citizen complaint map can be configured per tenant | CMS Enhancements | UI |  | Map theme configured for the tenant | Citizen complaint map shall render with the theme configured for that tenant | Pass
CMS/133 | Verify if ward names are displayed in the selected language on the citizen map | CMS Enhancements | Validation |  | Boundary localization seeded for the selected locale | Ward and boundary names on the citizen map shall be displayed in the selected language and not as codes or raw keys | Pass
CMS/134 | Verify boundary dropdown values and leaf level enforcement on the citizen complaint form | CMS Enhancements | Validation | Boundary hierarchy with duplicate codes across levels |  | Boundary dropdown shall not list duplicate options for the same code and the form shall not allow submission until the last (leaf) boundary level is selected | Pass
CMS/135 | Verify if map tooling and the map starting position are picked from the RAINMAKER-CMS.MapConfig master | CMS Enhancements | Functional |  | MapConfig master configured with a starting position for the tenant | Citizen and employee maps shall open at the configured starting position and shall use the configured map tooling, with no hardcoded city specific data | Pass
CMS/136 | Verify if the Complaint Type and Sub-Type dropdowns retain their values on the employee create-complaint form | CMS Enhancements | UI |  | Employee login | Selected complaint type and sub-type shall remain populated while filling the remaining fields and shall not become blank | Pass
CMS/137 | Verify if the location dropdown is displayed on the employee create-complaint form | CMS Enhancements | UI |  | Employee login; boundary data configured | Location / boundary dropdowns shall be displayed and shall load the configured boundary values | Pass
CMS/138 | Verify if the name of the employee who performed the last action is displayed in the timeline | CMS Enhancements | UI |  | Complaint with multiple workflow actions | Timeline shall resolve and display the acting employee name for each action | Pass
CMS/139 | Verify if the complaint details page displays the complete address and the type pickers are searchable | CMS Enhancements | UI |  | Complaint created with full boundary and address details | Complete address chain shall be displayed on the details page and the complaint type pickers shall support sorting and search | Pass
CMS/140 | Verify if mobile number validation on all surfaces is derived from the common-masters.MobileNumberValidation master | Mobile Validation | Validation | Valid and invalid numbers as per the configured regex | MobileNumberValidation master configured for the tenant with default set to true | Citizen UI, employee UI, employee profile, Configurator and MCP shall all accept and reject the same set of numbers as per the configured regex | Pass | Automated: Pass (employee-mobile-validator-447.spec.ts – valid mobile clears aria-invalid; invalid mobile surfaces help text and aria-invalid — both passed)
CMS/141 | Verify if real-time mobile number validation with a localized error message is shown on the create-complaint page | Mobile Validation | Validation | Number shorter and longer than the configured length |  | Validation message shall appear as the user types and shall be displayed in the selected language | Pass | Automated: Pass (login-mobile-input-validation.spec.ts – 5-digit number inline error + helper hint; employee-mobile-validator-447.spec.ts – real-time validation passed)
CMS/142 | Verify if the accepted mobile number length is derived from the configured regex | Mobile Validation | Validation | Numbers of different lengths | Static mobileNumberLength field no longer configured | Only the lengths permitted by the configured regex shall be accepted, with no reference to a separate length configuration | Pass
CMS/143 | Verify if mobile numbers entered with an optional leading zero are accepted | Mobile Validation | Validation | Number with and without a leading zero |  | Both formats shall be accepted by the fallback validator where the configured regex allows the trunk prefix | Pass
CMS/144 | Verify if the employee mobile number rule is taken from MDMS and not from a fixed 10 digit rule | Mobile Validation | Validation | Valid employee number that is not 10 digits | MDMS regex allowing a length other than 10 | Employee create and update shall accept the number as per the MDMS rule without a 10 digit restriction | Fail | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1558
CMS/145 | Verify if the user is able to log in through Keycloak using the authorization code flow with PKCE | Authentication | Functional | Valid and invalid Keycloak credentials | enable_keycloak flag set to true | User shall be redirected to the Keycloak login page, shall land on the application on valid credentials and shall be shown an error for invalid credentials | NA (Skipped) | Unable to verify
CMS/146 | Verify if logout terminates the Keycloak session as well as the application session | Authentication | Functional |  | Logged in through Keycloak | User shall be logged out of both sessions and shall be asked for credentials again on navigating back or reopening the application | Pass
CMS/147 | Verify if DIGIT native login continues to work when Keycloak is not enabled | Authentication | Functional |  | enable_keycloak flag set to false | Citizen and employee login through the DIGIT native flow shall work as before with no Keycloak redirection | Pass | Automated: Pass (citizen-otp-login.spec.ts – citizen can log in with OTP; login.spec.ts – employee login and bad credentials rejection verified)
CMS/148 | Verify platform admin login, dashboard and bootstrap wizard on the digit-ui-v2 application | Authentication | Functional |  | Platform admin credentials available | Platform admin shall be able to log in, view the dashboard and complete the bootstrap wizard steps | Pass | Automated: Pass (login.spec.ts – configurator login empty defaults verified; autocomplete-off attributes confirmed)
CMS/149 | Verify application behaviour when the session expires while the user is working | Authentication | Error Handling |  | Session left idle until the token expires | User shall be shown a re-login prompt or redirected to the correct login page of the same application, and the UI shall not hang on the expired token | Pass
CMS/150 | Verify if a login failure is shown as a readable message | Authentication | Validation | Wrong password, unregistered mobile number |  | A readable localized error message shall be displayed instead of a raw localization key | Pass | Automated: Pass (login.spec.ts – bad credentials rejected by employee login)
CMS/151 | Verify if the uploaded profile photo is displayed across the application and refreshes after an update | Authentication | UI | JPEG and PNG images |  | Photo shall be visible in the employee top bar and the citizen sidebar, and the avatar shall refresh immediately after saving Edit Profile | Pass | Automated: Pass (profile-photo-save-445.spec.ts – JPEG photo upload round-trip; profile-photo-save.spec.ts – photo upload round-trip)
CMS/152 | Verify profile photo upload with different image extensions and cases | Authentication | Validation | .jpg, .JPG, .jpeg and .png files |  | All supported formats shall upload successfully and render as a valid image with the correct file type | Pass | Automated: Pass (profile-photo-save-445.spec.ts – JPEG upload verified; profile-photo-save.spec.ts – photo upload round-trip verified)
CMS/153 | Verify if WhatsApp notifications are triggered for each complaint lifecycle event | Notifications | Functional | Create, assign, reassign, resolve, rate and escalate actions | Notification stack enabled; WhatsApp templates configured | A WhatsApp message shall be delivered to the complainant for each configured lifecycle event with the correct complaint number and status | Pass
CMS/154 | Verify if notification channel routing is driven by the MDMS notification configuration | Notifications | Functional | SMS only, WhatsApp only and multi-channel configuration | NotificationTemplate and NotificationRouting masters configured and the config driven flag enabled | Notifications shall be delivered only on the channels configured for that event and role, without any code change | Pass
CMS/155 | Verify if the legacy SMS message configuration continues to work for a tenant that has not opted into config driven notifications | Notifications | Functional |  | Config driven notification flag set to false | Existing SMS notifications shall continue to be delivered using the legacy localization message keys with no loss of messages | NA (Skipped) | Unable to verify, configurator ui does not have complete message displayed in logs
CMS/156 | Verify if OTP messages are delivered on the configured channel | Notifications | Functional | Citizen login OTP, employee forgot password OTP | OTP service enabled | OTP shall be delivered on the configured channel (SMS or WhatsApp) and shall allow successful login or password reset | Fail | https://github.com/egovernments/Citizen-Complaint-Resolution-System/issues/1559
CMS/157 | Verify if personally identifiable information is masked in the notification service logs | Notifications | Functional |  | Access to the notification log endpoint | Message content and provider response shall be masked in the logs and the default log level shall not expose message content | Pass
CMS/158 | Verify PII visibility for each role as per the configured security policy | Security | Functional | Complaint with name, mobile number, email and address | Security policy configured with the visibility grants for each role | Each role shall see the PII fields in plain or masked form exactly as configured, on the inbox, complaint details, assignee list and timeline | Pass | No implemented in Bomet, verified from moz azure setup
CMS/159 | Verify if the user is able to fetch boundary data directly from the map in addition to uploading an Excel template | Admin Onboarding | Functional |  | ADMIN login; Phase 2 of onboarding | User shall be able to either fetch boundaries from the map in one click or upload the Excel template, and both paths shall create the same boundary structure | Pass | Automated: Pass (boundaries-ui.spec.ts – search returns PW-prefixed boundaries; boundary-hierarchies.spec.ts – create and list verified)
CMS/160 | Verify if boundaries created during onboarding are saved against the city tenant | Admin Onboarding | Functional |  | Phase 2 boundary creation completed | Boundary data shall be created for the city tenant and shall not be written to the state root tenant | Pass | Automated: Pass (boundaries-ui.spec.ts – PW-prefixed boundaries created through onboarding searchable)
CMS/161 | Verify boundary search behaviour against the configured search limit | Admin Onboarding | Functional | Search returning more results than the configured limit | Boundary search limit configured | Search shall return results within the configured limit and shall indicate that the results are limited instead of failing | Pass | Uniable to verify time limit exceeded case
CMS/162 | Verify if the user is able to continue onboarding using an existing tenant | Admin Onboarding | Functional |  | Existing tenant available; Phase 1 of onboarding | User shall be able to select the existing tenant and proceed with the remaining phases without recreating the tenant | Pass
CMS/163 | Verify the default jurisdiction hierarchy on the employee onboarding phase | Admin Onboarding | Validation |  | Phase 4 of onboarding | Jurisdiction hierarchy shall default to ADMIN and shall be editable by the user | Pass
CMS/164 | Verify bulk employee upload validation when the master data is only partially available | Admin Onboarding | Error Handling | Bulk employee template with valid rows | Partial MDMS master fetch | Valid rows shall not be reported as invalid; any genuine validation error shall be reported with the correct row and reason | Pass | Automated: Pass (employees.spec.ts – list renders, search narrows, status filter partitions; create happy path; bulk import 3 valid + 2 invalid rows)
CMS/165 | Verify the re-login behaviour when the session expires during boundary creation | Admin Onboarding | Error Handling |  | Session expired while on the boundary creation step | Re-login prompt shall be displayed and shall clear correctly after login so that the user can continue the boundary creation | Pass
CMS/166 | Verify employee update after navigating back and forth on the employee form | Admin Management | Error Handling |  | Existing employee record being edited | Employee update shall complete successfully without an error caused by stale form data or a missing reactivate flag | Pass
CMS/167 | Verify if boundary maps are displayed in the Management view | Admin Management | UI |  | Boundary data available for the tenant | Boundary map shall be rendered in the management view with the correct polygons for the tenant | Pass | Automated: Pass (boundaries-ui.spec.ts – search returns boundaries created via wizard)
CMS/168 | Verify if the Org Chart displays the employee reporting hierarchy | Admin Management | UI |  | Employees created with reporting relationships | Org chart shall display the reporting hierarchy correctly and shall reflect changes made to the reporting structure | Pass
CMS/169 | Verify pagination behaviour on the master data list screens | Admin Management | Functional | Master data with records exceeding one page |  | Records shall be fetched page by page from the server, navigation across pages shall work and the total count shall be correct | Pass | Automated: Pass (complaints.spec.ts – offset-based pagination _search verified)
CMS/170 | Verify if the user is able to view and edit all configured locales together in the localization list | Admin Management | Functional | Localization value in more than one language | More than one locale configured | All locales shall be displayed side by side for a key and the user shall be able to edit and save them together | Pass | Automated: Pass (localization.spec.ts – inline edit saves localization values across locales)
CMS/171 | Verify if the Configurator UI is displayed in the selected language | Admin Management | Validation | en, hi, fr, pt |  | List column headers, page titles, resource labels and all UI text shall be displayed in the selected language with no raw localization keys | Pass | Automated: Pass (localization.spec.ts – tenant parity, upsert verified; hardcoding.spec.ts – no tenant-specific hardcoding detected)
CMS/172 | Verify if the existing theme configuration records are displayed and can be edited | Admin Management | Functional |  | Tenant with a legacy theme configuration record | Legacy theme records shall be visible in the list and shall be editable and saved successfully | Pass
CMS/173 | Verify if department and designation localizations are written to the correct localization module | Admin Management | Functional |  | Department and designation created from Configurator | Localization entries shall be created under the common localization module and the names shall render correctly on the CMS employee screens | Pass | Automated: Pass (localization-modules.spec.ts – department and designation localizations in rainmaker-common, not rainmaker-common-masters)
CMS/174 | Verify if the complaint status is displayed consistently across all surfaces | Core UI | Validation | Complaint in each workflow state |  | The same status label shall be displayed on citizen UI, employee UI, inbox, complaint details, dashboard and notifications for a given state | Pass | Automated: Pass (complaint-detail-page.spec.ts – citizen detail page loads; pgr-details.spec.ts – status/classification all render correctly)
CMS/175 | Verify toast message behaviour across the application | Core UI | UI | Success and error toasts |  | Toast shall auto dismiss after the configured duration and shall also be closable using the close button, with consistent behaviour on citizen and employee UI | Pass
CMS/176 | Verify the earlier reported UI defects on the citizen and employee screens as a regression check | Core UI | UI |  | Complaint created with full address details | Address shall include the city / tenant value, input fields and the inbox date range control shall be correctly sized, the header logo shall not be stretched and an invalid profile email shall be rejected | Pass | Automated: Pass (citizen-home-page.spec.ts – /all-services and /pgr-home render correctly; complaint-detail-page.spec.ts – detail page loads without crashing)